Innovation Patterns in the World Bank Group Portfolio

A Pilot Analysis of IEG Evaluations for Lending Operations

Natalia Agapitova

Anastasia Nedayvoda

Stephen Winkler

Amschel de Rothschild

Ergun Ertekin

Sarah Lenoble

Abstract: This paper employs large-scale text analytics and generative-AI methods to analyze innovation patterns within the World Bank Group (WBG) portfolio. It draws on over 7,500 Independent Evaluation Group (IEG) project evaluations completed between 1998 and 2025. The study finds that, on average, innovative projects are associated with higher performance outcomes. It also identifies several key enabling factors for innovation at the WBG, including: disciplined experimentation, flexible and adaptive project designs, contextualization to local settings, participatory approaches in the design and piloting of new solutions, and visionary and supportive internal leadership. The analysis reveals that innovation within the WBG has evolved over time from sporadic experimentation to an embedded organizational capability. However, significant constraints persist such as bureaucratic fragmentation, capacity gaps, overly complex project designs, lack of continuity in scaling innovations, and insufficient incentives for learning and adaptation.

JEL: C45, C55 031, O19

This version: April 19, 2026

Table of Contents

Abbreviations and Acronyms	4

1.	Introduction	5

2.	Methodology	7

A.	Dataset	8

B.	Tools and Environments Used	9

C.	Core Elements of the Analysis	9

D.	Workflow	10

E.	Lessons Learned from the Use of Generative AI Tools	11

3.	Innovation in Lessons of WBG Lending Portfolio	12

A.	History of Innovation Dynamics	12

B.	Types of Innovations	15

C.	Innovation Patterns in Different Geographies	18

D.	Innovation Patterns in Different Settings	20

E.	Innovation Patterns in Different Sectors	21

F.	Technology Premium	24

G.	IFC Collaboration and Innovation Patterns	25

H.	Private Capital Mobilization	26

I.	Role of Donors and Trust Funds in Innovation	27

4.	Lessons from the Portfolio Analysis	28

A.	Key Drivers of Performance in Innovative Projects	28

B.	Contextual and Participatory Drivers of Innovation	29

C.	Institutional and External Drivers of Innovation	31

D. Looking Ahead: Fostering Strategic and Scalable Innovation	32

5.	Data Gaps and Future Research Directions	32

6.	Conclusion	35

Bibliography	36

Appendix A. Detailed Steps in the Workflow	37

Appendix B. Innovation Keyword Dictionary	39

Appendix C. Select Hypotheses Tested	41

Appendix D. Evolution of Innovation Practices at the World Bank Group	44

Appendix E. Tracing the Diffusion of Innovation Models	48

Diffusion of Public-Private Partnership Model: Key Milestones and Evidence	49

Diffusion of CDD Model: Key Milestones and Evidence	50

Appendix F. Diffusion of Innovation Models in Fragile versus Non-Fragile Context	53

# Abbreviations and Acronyms

AI		Artificial Intelligence

API		Application Programming Interface

APL		Adaptable Program Loan

CAPEX 		Capital Expenditures

CDD		Community-Driven Development

DPL		Development Policy Loan

ESF		Environmental and Social Framework

FCS		Fragile and Conflict-Affected Situations

FCV		Fragility, Conflict and Violence

GenAI		Generative Artificial Intelligence

GIS		Geographic Information System

IBRD		International Bank for Reconstruction and Development

ICR		Implementation Completion and Results Report

ICRR		Implementation Completion and Results Report Reviews

ICT		Information, Communication and Technology

ID		Identification

IDA		International Development Association

IEG		Independent Evaluation Group

IFC		International Finance Corporation

LIL		Learning and Innovation Loan

LLM		Large Language Model

M&E		Monitoring and Evaluation

MDGs		Millennium Development Goals

MIGA		Multilateral Investment Guarantee Agency

MFD		Maximizing Finance for Development

MPA		Multiphase Programmatic Approach

NGO		Nongovernmental Organization

PCM		Private Capital Mobilization

PFM		Public Financial Management

PforR 		Program-for-Results

PPAR		Project Performance Assessment Review

PPP		Public-Private Partnership

PSW		Private Sector Window

SDGs		Sustainable Development Goals

STEP		Systematic Tracking of Exchanges in Procurement

TTL		Task Team Leader

# Introduction

Innovation has become a central feature of the World Bank Group’s (WBG) development practice, yet until now it has remained difficult to analyze systematically across the portfolio.  By analyzing over 7,500 lending project evaluations completed between 1998 and 2025, this paper offers the first large-scale, evidence-based view of how innovation has been used, evolved, and scaled in WBG lending operations over the past three decades. By linking innovation patterns to project performance, supervision quality, monitoring and evaluation, and scaling dynamics, the analysis helps move the discussion beyond isolated success stories toward portfolio-level learning. The findings have direct operational relevance: they inform how teams can design and sequence innovations more effectively, how risks can be managed through piloting and adaptive implementation, and how institutional conditions—such as leadership, flexibility, and collaboration—shape outcomes. More broadly, this analysis lays the groundwork for treating innovation as a measurable and manageable development lever, supporting strategic decision-making, cross-sector learning, and more deliberate investment in approaches that translate novelty into sustained impact.

Defining innovation in the WBG context poses a fundamental challenge: there is no single, formal institutional definition, and what counts as “innovative” has shifted markedly as development practice, technology, and client capabilities have evolved. An approach that was novel in the 1990s—such as community-driven development or electronic procurement—may now be considered standard practice, while newer forms of digital, financial, or collaborative innovation continue to emerge. This paper builds on foundational frameworks from development studies, organizational theory, and innovation management, and adopts an empirical, practice-based perspective rooted in how innovation is described, assessed, and learned from project evaluations themselves. Drawing on the narrative evidence, innovation is broadly understood as systematic application of new ideas, methods, and technologies to address complex social, economic, and environmental challenges in ways that create measurable improvements in development outcomes. This allows the analysis to reflect both temporal change and contextual variation, capturing innovation as a dynamic process shaped by evolving development challenges, institutional learning, and organizational incentives, rather than as a fixed label or one-size-fits-all concept.

Leveraging generative artificial intelligence (GenAI) and advanced data analytics, the study examines three key questions: 1) how has innovation evolved across sectors, regions, and instruments? 2) What factors enable or constrain innovation? and 3) Does innovation contribute to improved development outcomes? The analysis investigates whether higher “innovation intensity” – concentration of innovative approaches in WBG operations – is associated with stronger results or simply with greater variance and risk. It explores the organizational and contextual factors that enable innovation to succeed, assessing how supervision quality, monitoring and evaluation (M&E) rigor, and adaptive implementation arrangements interact to either amplify or moderate innovation outcomes.

Findings show that innovation is increasingly integral to the WBG’s agenda and that innovation transitioned from isolated pilot initiatives in the 1990s to integrated, multi-dimensional strategies by the 2010s and 2020s. This institutional evolution has improved the replication and scaling of successful approaches and strengthened the WBG’s capacity to translate experimentation into sustained impact. This shift aligns with institutional reforms, increased use of digital technologies and global policy agendas emphasizing learning, flexibility, and results-based management. Innovative projects, particularly those that combine operational redesign with digital or financial solutions, are associated with higher performance ratings and demonstrate greater sustainability. Together, these findings suggest that innovation within the WBG has matured from sporadic experimentation into a more frequent organizational capability. However, the results also surface factors that continue to constrain innovation, including bureaucratic fragmentation, capacity gaps, overly complex project designs, lack of continuity in scaling innovations, and insufficient incentives for learning and adaptation.

The paper introduces an Innovation Index that helps to assess projects’ innovativeness, and an innovation taxonomy that classifies innovations into four categories: operational/institutional, technological, financial, and collaborative. The analysis emphasizes the importance of aligning technological complexity with local capacity, embedding collaboration and learning in project design, and maintaining flexible structures that allow for iterative adaptation. The study also lays the groundwork for a structured, searchable innovation portfolio and outlines a roadmap for further research to enhance innovation management and its contribution to development effectiveness across the WBG.

Evidence from the project evaluations points to a consistent pattern: innovations are more associated with scale-up language when they are designed as adaptive learning processes rather than one-time experiments. The most effective innovations began with small, testable pilots, integrated real-time feedback loops, and scaled gradually as capacity and ownership were built, and results were demonstrated. Collaborative aspects of innovations – those engaging government, private sector, and civil society partners – were especially effective at sustaining outcomes, particularly in fragile and low-capacity contexts. Conversely, overly complex or rigid designs without flexibility for adaptation often hindered adoption in new contexts. Strong leadership, continuity in task teams, and rigorous supervision further increase the likelihood that innovative components deliver tangible, lasting impact.

In addition to the empirical findings, this paper contributes to literature on public sector innovation by showing how innovation can be analyzed at scale without sacrificing contextual nuance. The paper offers a replicable framework for measuring, comparing, and tracing innovation in complex organizations. While many prior studies rely on small samples or case studies, this paper systematically analyzes thousands of project evaluations to quantify innovation trends, types, and outcomes. It advances the field by developing an Innovation Index and a taxonomy tailored to the development context, and by leveraging AI-driven analytics to extract insights from unstructured data. This integrated approach not only enhances institutional learning but also offers a model for evidence-based innovation management across development organizations. In a rapidly evolving global landscape, shaped by climate urgency, fragility, and digital transformation, the ability to systematically identify what works, where, and why positions the WBG to lead in translating innovation into measurable and sustainable development impact.

This study was designed and implemented as a rapid prototype to provide exploratory analyses using a practical approach built for iteration The team developed the analysis to assess the feasibility and value of using GenAI tools to analyze and build knowledge on innovation across the WBG portfolio. This initial approach demonstrated a strong ability to classify past projects as innovative, drawing on an LLM-generated and human-validated corpus of innovation keywords that could be applied consistently at scale. It generated portfolio-wide insights that would be difficult to produce through manual review alone. At the same time, reliance on known keywords introduces important limitations: it can under-detect innovations described in context-specific language, can be better suited to retrospective analysis than prospective analysis, and may miss forms of innovation that are embedded in practice rather than labeled explicitly. Future iterations could build on these findings by exploring hybrid approaches that combine keyword matching with semantic similarity methods (e.g., embeddings) or guided LLM classification to reduce dependence on a fixed dictionary (Lewis et al. 2020; Reimers and Gurevych 2019). As project evaluations have a lagged timeline, expanding the corpus of data along with the methodology would also allow for more timely analysis of incoming projects. Finally, future analysis should engage thematic and sectoral experts to test how innovation varies by context and to refine the methodology accordingly. The findings described in this paper are exploratory and descriptive; the methodology is not designed to identify causal relationships.

# Methodology

In development organizations, innovation is increasingly recognized as a multi-dimensional phenomenon, requiring both conceptual clarity and operational adaptability to address complex challenges (Crossan and Apaydin 2010; Damanpour and Aravind 2012; OECD/Eurostat 2018; Rogers 2003). The literature identifies several factors that enable innovation and scaling of innovation, especially in large organizations and government agencies. Internal leadership and organizational culture are critical: visionary leaders and a climate that encourages experimentation and risk-taking foster innovation (Crossan and Apaydin 2010; O’Reilly and Tushman 2013). Team capabilities, incentives, and a learning orientation empower staff to pursue creative solutions (Farnese et al. 2019). Recent reviews frame innovation as an organizational capability shaped by enabling conditions such as leadership commitment, incentives for experimentation, and risk-tolerant cultures, while constraints include bureaucratic rigidity, fragmented knowledge flows, and short project cycles (Borins, 2014; Bason, 2018; OECD, 2017). Scaling and institutionalization remain persistent challenges: pilots often succeed but diffusion across portfolios is uneven and vulnerable to discontinuity when champions depart or resources shift (Hartley, 2005; Kattel & Mazzucato, 2018). Innovations that are designed to be modular and adaptable, together with flexible management processes that support iterative piloting and rapid adjustment, are more likely to scale successfully (Bruno et al. 2019; Cooley and Linn 2014). Robust monitoring, evaluation, and adaptive learning are essential for refining approaches, mitigating risks, and building the evidence base needed for expansion (Barker, Reid, and Schall 2015; Ramalingam, Laric, and Primrose 2014). Ultimately, for innovation to generate improved development outcomes it must move from pilot to scale, with institutionalization, local ownership, and adequate financing as prerequisites for sustainability (Linn 2012; Schut, Leeuwis, and Thiele 2020; Woltering et al. 2019). This conceptual framework guided the formulation of evaluative questions and hypotheses.

The methodology was built on the conceptual foundations of the literature review and combined GenAI tools, Python-based text mining, and structured project-level evaluation data, guided by subject-matter experts. It aimed to determine whether AI-assisted text analysis could reliably surface insights on how innovation for development is defined, as well as how innovative solutions are designed, implemented, and disseminated across the lending portfolio. In addition to the key research questions, the study aims to: (i) assess whether this integrated approach of combining GenAI, coding, and database queries can provide a replicable and scalable workflow for mining institutional data, including for lessons and analyses that go beyond innovation; and (ii) evaluate the effectiveness of GenAI tools in research and analytical work on the loosely defined topic of corporate innovation.

The findings provide not only a substantive assessment of innovation in World Bank projects, but also a demonstration of an iterative workflow to support evidence-based learning. At the same time, the study serves as a testing ground for GenAI itself, illustrating both its current capabilities and potential for streamlining the identification and dissemination of effective innovation practices across the WBG.

## Dataset

The Independent Evaluation Group’s (IEG) public dataset contains data from 8,569 Implementation Completion and Results Report Reviews (ICRRs) and selected Project Performance Assessment Reviews (PPARs) covering project evaluations from 1998 to 2025. This dataset represents the full corpus of World Bank projects approved and evaluated since the 1990s. The analysis draws on a project-level dataset of 7,574 unique operations. A ‘one project, one record’ dataset was constructed by grouping evaluations by project code (known as P-code) and keeping a single document of record per project: if a PPAR exists, it was used; otherwise, the ICRR was retained. This process yielded 1,113 projects represented by a PPAR and 6,461 by an ICRR. For the 993 projects that had both, the PPAR was used for the reasons outlined in Box 1.1.

The IEG dataset was chosen as the foundation for this analysis due to its combination of quantitative consistency and qualitative richness tracing how innovations evolve and scale. For each operation the file captured core identifiers: P-code, country, Global Practice (GP), region, lending instrument, International Bank for Reconstruction and Development (IBRD), International Development Association (IDA),  blend, Fragility, Conflict and Violence (FCV) flag, lifecycle dates (approval and closing fiscal years), and IEG ratings for outcomes, supervision, monitoring and evaluation, and risk. Importantly, this dataset included the full “Lessons Learned” section of the reports, comprising over five million words of narrative evidence that we mined to understand the evolution of innovation practices and patterns across the World Bank lending portfolio.

# Box 1.1. Overview of Implementation Completion and Results Reports and Project Performance Assessment Reports

An ICRR is the IEG validation of the World Bank team’s self-evaluation (the ICR) for a closed project. Prepared by IEG, the ICRR reviews the evidence presented in the ICR and related project files, may involve consultation with the last Task Team Leader (TTL), and provides independent ratings on Outcome, Risk to Development Outcome, Bank Performance, and Quality of M&E. It is a desk-based product to ensure consistency and credibility across the World Bank’s results reporting.

An ICRR typically covers project data; objectives and components; relevance; achievement of objectives against the results framework; efficiency; overall outcome rating; risk to development outcome; World Bank performance; quality of M&E; lessons learned; and whether a fuller field assessment is recommended.

PPARs are IEG’s selective, field-based, follow-up evaluations undertaken for a subset of projects where deeper learning value is expected. PPARs triangulate evidence through country missions and stakeholder interviews and provide richer analysis while confirming or updating ratings.

In summary, every lending project receives an ICR prepared by World Bank management and an ICRR prepared by IEG; a smaller number of projects receive a PPAR for more in-depth, on-the-ground assessment.

## Tools and Environments Used

We used GenAI tools and Python libraries to complete the analysis. GenAI tools were used to: (i) conduct the literature review (Elicit and Perplexity), and (ii) test the quality of outputs by submitting identical requests to multiple tools and comparing results; (iii) cross-check logic by asking one tool to review or refine the output of another (for example, proposed hypotheses); and (iv) assess responsiveness to prompting, since identical instructions can yield different outputs across models, including differences between commercial and open-source providers (DeepSeek V3, GPT-4o, GPT-5). Python libraries were used for most of the quantitative analyses (e.g., counting the occurrences of terms) given the proven tendency of large language models (LLMs) to hallucinate when handling the quantitative analysis of large datasets. This approach provided clear reproducible metrics, coupled with manual due diligence and quality controls.

## Core Elements of the Analysis

Eight core elements were used to map and analyze innovation across the portfolio:

- Innovation Keyword Dictionary: In the absence of a clear definition of innovation, different LLMs were prompted to generate lists of ~200 innovation-related terms, drawing on their knowledge of innovation practice and international development. The lists were combined, duplicates removed, and the resulting pool reviewed and verified by the authors as well as through automated sensitivity checks, with edits made following review. Future research could explore how to better calibrate models to capture sector-specific terminology. The final keyword list is presented in Appendix B.

- Innovation Index: Python scripts scanned each lesson to count occurrences of innovation keywords. Based on these counts, we assigned projects an innovativeness score of High, Moderate, or Low. We grouped projects rated High and Moderate to create a subset of “innovative” projects. This Innovation Index was used to trace the evolution of innovativeness, map its distribution across GPs and regions, and test scaling patterns by linking High/Moderate projects to the presence of pilot or scale-up language.

- Innovation Taxonomy: From the “innovative subset,” the authors prompted LLMs to surface prominent types of innovation. These were iteratively reviewed and refined into a four-part Innovation Taxonomy (Table 3.4).

- Iterative Human–Model Reasoning: A central methodological step involved an iterative reasoning process carried out by GenAI models and the authors. Rather than treating model outputs as static findings, we engaged them in a sustained exchange: running dozens of exploratory prompts, parsing long outputs, and revising lines of inquiry in response. This process surfaced candidate patterns, stress-tested preliminary insights, and generated alternative framings that would have been difficult to reach through manual review alone. We conducted targeted literature review searches and consulted experts to guide the models by suggesting new directions and filtering out irrelevant outputs.

- Hypothesis Formulation: Building on this iterative reasoning, we distilled the most analytically valuable lines of inquiry into hypotheses. At this stage, LLMs helped refine wording and propose possible validation strategies. The resulting hypotheses (see Appendix C) combine the computational breadth of LLM-assisted mining with the interpretive depth of human analysis, yielding structured questions that could be meaningfully tested against the portfolio evidence.

- Hypothesis Testing: The hypotheses tested are presented throughout the paper. At the outset (May–June 2025), quantitative validation relied primarily on Python, given concerns about hallucination in GenAI models.

- Contextualizing Metrics through Institutional Knowledge: After producing quantitative outputs (e.g., rankings, sectoral and regional breakdowns, and time series), LLMs generated narrative interpretations. Prompts guided LLMs to describe the numbers and to interpret them using their broad knowledge of World Bank reforms, institutional change, and global development history. This step helped to connect portfolio-level patterns with institutional changes. All narrative outputs were then manually cross-checked against the underlying data, supplemented with illustrative project examples, and reviewed and validated by the authors.

- Top Innovation Models: LLMs were prompted to identify candidate innovation models, defined as distinct products and services that began as localized pilots and subsequently scaled across countries and sectors. The authors refined this list to ensure institutional relevance. Python was used to count and normalize mentions of these models in project lessons, controlling for multiple mentions within each project. This enabled us to track the trajectory of these innovations from isolated experiments to mainstream features of World Bank operations. Appendix D details how these diffusion patterns form a quantitative fingerprint of institutional learning.

## Workflow

A structured workflow was designed to extract, classify, and interpret evidence of innovation across the World Bank’s portfolio (see Appendix A). This approach addressed two challenges. First, without a structured workflow, the generation of insights would depend on ad hoc GenAI prompting or human reading—methods that yield variable findings and lack the consistency and rigor needed for systematic evidence. Second, mainstreaming innovation requires systematic, transparent methods to identify patterns and track diffusion across time, regions, and sectors. A replicable workflow lays the foundation for future analytics with reduced manual intervention.

The workflow was assembled through iterative experimentation, combining Python coding, LLM capabilities, and expert validation. The workflow design was modular, with each step functioning as a discrete building block that could be reused or recombined depending on the research question. This logic ensured flexibility while preserving analytic coherence and aligning the sequence of steps aligned with the core elements of analysis outlined in section 2.C.

The initial workflow used human assistance to operate effectively; the long-term goal is to integrate it into internal WBG systems for a greater degree of automation. Embedding the modules into corporate databases and orchestrating them through standardized pipelines would allow continuous updating of innovation insights as new data sources are introduced. Over time, this could evolve into a semi-automated monitoring system, linking LLM text parsing, Python scripts, and structured databases. The modular design also makes it adaptable—specific blocks, such as keyword tagging or taxonomy generation, can be repurposed for other themes (e.g., climate, fragility, governance), broadening the WBG capacity to systematically mine lessons from its vast knowledge base.

## Lessons Learned from the Use of Generative AI Tools

Across all stages of the study, GenAI added value as a complement to coding and expert analysis. It accelerated keyword scanning, broadened reasoning, proposed hypotheses and validation methods, and enriched the interpretation of results. Its effectiveness was greatest when paired with expert direction and review. The demonstrated ability to now deliver reliable portfolio analytics further underscores its potential. Used together, Python and GenAI can act as force multipliers—augmenting, rather than replacing, staff expertise.

An iterative human–model reasoning helped, on one hand, systematize and interpret large volumes of data (GenAI), and, on the other, parse, prioritize, and direct large volumes of text (human). At initial stages of the analysis, LLM produced implausible institutional linkages, underscoring the need for oversight. The pilot highlighted the need to establish a shared method for filtering or structuring large volumes of model output.  Once iterative reasoning narrowed the field, LLMs proposed structured hypotheses and corresponding validation strategies. Most of these strategies echoed established methods, yet several extended them in logically meaningful ways. The outputs were sufficiently precise to be implemented directly into coding, though about one-third of hypotheses collapsed when tested against the data. This reinforces the importance of human review and data-grounding to separate promising leads from ideas that cannot be operationalized.

The use of GenAI in narrative contextualization also proved promising when models were guided with references to reforms, strategies, or global agendas. They generated case-like accounts that linked diffusion patterns to external factors, which were particularly effective for decade-level comparisons and performed well in enriching quantitative tables with interpretive depth. However, they were less reliable in capturing finer institutional changes and occasionally missed nuance. Extending the analysis to non-public institutional data would further strengthen GenAI performance.

This study was conducted in a six-months timeframe as a rapid prototype. While it demonstrated that GenAI can accelerate text mining and hypothesis generation, model outputs required systematic cross-checking to avoid hallucinations and misclassification. We therefore used Python coding to calculate quantitative metrics and LLMs primarily for thematic interpretation and hypothesis framing. Manual validation by subject-matter experts was critical at multiple stages. In addition, though the workflow sequence was tested for the innovation use case, its generalizability to other thematic areas will require further piloting. While the initial analysis provides valuable insights, it also surfaces limitations and points to areas for future research and improvement, which are detailed in chapter 5.

# Innovation in Lessons of WBG Lending Portfolio

## History of Innovation Dynamics

Over the past three decades, World Bank projects have increasingly prioritized innovation. Though references to innovation were rare in project lessons during the late 1990s and early 2000s, by the 2010s and 2020s, innovation became more visible and documented, reflecting a broader recognition of its role in driving development impact (Table 3.1, Figure 3.1). The World Bank’s innovation approach has evolved from isolated, modest experiments to integrated, multi-dimensional strategies supported by new financing tools, such as the Adaptable Program Loan (APL), Standard Operating Procedure (SOP), or Multiphase Programmatic Approach (MPA). The analyzed project lessons highlight the World Bank’s growing role as a global knowledge broker while also customizing solutions to diverse contexts, ensuring innovations contribute to sustainable development impact. A more detailed discussion on historic trends is provided in Appendix D.

The share of innovative projects in the Bank Group portfolio has more than doubled over two decades, rising from 6.7 percent in 1998–2002 to about 18 percent in 2018–22 (Table 3.1, Figure 3.1). This upward trend reflects a gradual institutional shift toward more consistent embedding of innovation across operations, though low-innovation projects still account for the large majority (above 75 percent).

Table 3.1. Evolution of Innovation Intensity in Bank Group Projects (5-Year Cohorts, 1998–2025)

| Cohort | High + Moderate Innovative Projects (Number) | High + Moderate Innovation (%) | Low Innovative Projects (Number) | Low Innovation (%) |
| --- | --- | --- | --- | --- |
| 1998-2002 | 75 | 6.7% | 1039 | 93.3% |
| 2003-2007 | 121 | 8.4% | 1326 | 91.6% |
| 2008-2012 | 134 | 11.8% | 1003 | 88.2% |
| 2013-2017 | 225 | 13.6% | 1424 | 86.4% |
| 2018-2022 | 242 | 17.7% | 1122 | 82.3% |
| 2023-2025 | 177 | 20.5% | 686 | 79.5% |

Note: The time period 2023–2025 is a partial cohort, with many projects still under implementation.

Figure  3.1. Evolution of Innovation Intensity in WBG Projects (5-year cohorts, 1998-2025)

Building on these trends, table 3.2 contextualizes the evolution of innovation intensity by linking the observed rise in innovative projects to major institutional milestones and external global agendas. Each five-year cohort corresponds to shifts in Bank Group instruments and strategies, from the introduction of Learning and Innovation Loans (LILs) in the late 1990s, to results-based financing and PforR in the 2000s and 2010s, and the Environmental and Social Framework (ESF) and COVID-19 fast-track responses between 2018–2022. At the same time, it situates these internal shifts within broader global movements, including the Millennium Development Goals (MDGs), aid effectiveness compacts, Paris Agreement, Sustainable Development Goals (SDGs), and climate finance mechanisms. The table underscores that the growth of innovation in Bank Group operations has been shaped by both internal reforms and external global agendas.

Table 3.2. Contextualizing the Innovation Intensity of Bank Group Projects Over Time

| Cohort | Share of High + Moderate Innovative Projects (%) | Key Bank Group institutional milestones that likely shaped innovation density | External global agendas and innovation movements that reinforced the trend |
| --- | --- | --- | --- |
| 1998-2002 | 6.7% | Launch of LILs to pilot novel approaches; Comprehensive Development Framework pushes country-owned, holistic strategies and “results” language. | Millennium Development Goals (2000) sharpen the focus on measurable outcomes; progress towards open data and digital government initiatives; surge of mobile phone use. |
| 2003-2007 | 8.4% | Global Partnership on Output-Based Aid (later renamed Global Partnership for Results-Based Approaches) mainstreams “results-based” and “pay-for-results” pilot financing models (2003); Development Policy Lending (2004; Operational Policy 8.60) consolidates policy reform budget support; pilot use of country systems in procurement begins. | Paris Declaration (2005) and Accra Agenda for Action (2008) formalize principles of alignment, managing for results, and mutual accountability. |
| 2008-2012 | 11.8% | Climate Investment Funds (2008) channel concessional climate windows through the Bank Group; Open Data (2010); PforR (2012) ties disbursements to verified results. | Global financial crisis demands counter-cyclical and innovative financing approaches; Busan Partnership for Effective Development Cooperation (2011) broadens effectiveness agenda; Green Climate Fund established (2010). |
| 2013-2017 | 13.6% | Twin Goals/Bank Group Strategy (2013); risk-based Investment Project Financing policy and Systematic Country Diagnostics and Country Partnership Frameworks (2014) sharpen selectivity; reorganization of GPs (2014) improves knowledge flows; new Procurement Framework (2016) adds “fit-for-purpose” flexibility; MPA (2017) enables phased learning; Maximizing Finance for Development (MFD)/Cascade approach (2017) and IDA18 Private Sector Window (PSW, 2017) crowd-in private solutions. | Paris Agreement (2015) reinforces global climate commitments |
| 2018-2022 | 17.7% | ESF goes live (2018); procurement reform fully operational; GovTech Partnership (2019) and Digital Economy for Africa (DE4A) (2018) elevate digital transformation and state capability agendas; COVID-19 fast-track and MPA scale-up programs (2020) normalize agile, programmatic operations; Window for Host Communities and Refugees (WHR) established as a dedicated IDA financing window | SDGs (2015 onward) drive scale; COVID-19 pandemic shock (2020) accelerates digital delivery and adaptive management; climate finance gains renewed momentum through Climate Investment Funds and Green Climate Fund replenishments. |
| 2023-2025 | 20.5% | Evolution Roadmap (2023) resets Bank Group mission toward addressing global challenges and proposes changes to operating model and finance; renewed decentralization push (2025). Trust Fund Umbrella 2.0 consolidation matures. | Mid-course pressure to accelerate SDG progress; climate finance scale-up and reform debates among multilateral development banks. |

Note: The time period 2023–2025 is a partial cohort.

Next, we examined if and how innovation was operationalized through pilots and subsequently scaled up to assess whether the World Bank leverages successful innovation for broader, sustained impact or if promising innovations remain as isolated pilots. Piloting has long been a core mechanism for testing new approaches, yet the way projects document and connect pilots to scaling has evolved more unevenly than overall innovation intensity. Examining pilot and scale-up language offers a complementary lens to understand the World Bank’s gradual shift from isolated experimentation towards embedding scalable solutions in its operations.

Over the past two decades, references to pilots in World Bank projects have remained fairly steady while the share of pilots that do not mention scaling has steadily decreased.. In the late 1990s and early 2000s, innovation efforts rarely referenced pilots, and even fewer linked them to scaling (Table 3.3). Since then, pilot mentions have increased modestly: from 7.9 percent of projects in 1998–2002 to 12.5 percent in 2018–2022, with 10.4 percent in the partial 2023–2025 cohort. Over time, the share of isolated pilots – those that are not connected to any mention of scaling – has dropped from 72.7% in 1998-2002 to 54.4% today. Figures for the 2023–2025 period should be interpreted cautiously, as many projects are still under implementation and lack final evaluation data. Unless otherwise noted, all time-series are grouped by the fiscal year of the evaluation.

Appendix E summarizes the diffusion of innovation ‘models’ at the WBG. We define innovation models as a proven, archetypal approach that embodies a distinctive method for addressing a development challenge through novel products, services, processes, or organizational practices. Our analysis identified innovation models that originated as pilots, evolved into working prototypes, and were adopted and scaled across diverse contexts and geographies. Examples include the private-public partnership model, community-driven development (CDD), conditional cash transfers (CCT), and e-procurement.

# Table 3.3. Innovation Scaling Patterns in World Bank Lending

| Cohort | Total projects | With pilot | With pilot and scale in same lessons | % of all projects with pilot | % of pilots that do not mention scaling |
| --- | --- | --- | --- | --- | --- |
| 1998-2002 | 1114 | 88 | 24 | 7.9% | 72.7% |
| 2003-2007 | 1447 | 137 | 49 | 9.5% | 64.2% |
| 2008-2012 | 1137 | 107 | 38 | 9.4% | 64.5% |
| 2013-2017 | 1649 | 171 | 75 | 10.4% | 56.1% |
| 2018-2022 | 1364 | 170 | 68 | 12.5% | 60% |
| 2023-2025 | 863 | 90 | 41 | 10.4% | 54.4% |

Note: The time period 2023–2025 is a partial cohort, with many projects still under implementation. The figures indicate how projects are framed in evaluative narratives, but do not provide verified evidence of pilots transitioning to scale.

## Types of Innovations

A taxonomy of innovation reveals broader patterns in projects that might otherwise appear as isolated experiments. Over the past three decades, World Bank projects have introduced new delivery systems, technologies, financing tools, and collaborative models across diverse contexts, with varying degrees of success. By grouping these approaches into four broad families, table 3.4 highlights both the range of innovations in the portfolio and the conditions under which they have taken root. This lens enables comparison of experiences across sectors and regions, highlighting interactions among different types of innovation and tracing the World Bank’s evolving capacity to turn pilots into scalable solutions.

# Table 3.4. Taxonomy of Innovations in the World Bank Portfolio

| Innovation Type | Examples and Features | Contexts Where Successful |
| --- | --- | --- |
| Operational/Institutional | New delivery systems, transparency and accountability mechanisms (e.g., e-governance and e-procurement) | All sectors, especially complex or fragile environments |
| Technological | Digital services (e.g., telemedicine) | Middle-income geographies; urban, governance, and health sectors |
| Collaborative | Multi-stakeholder coalitions, CDD, self-help groups | Fragile, rural, and natural resource projects |
| Financial | Fintech, psychometric testing, output-based financing, community funds | Infrastructure, financial inclusion, service delivery, urban or rural |

Operational and institutional innovations focus on re-engineering delivery arrangements to improve the quality, effectiveness, and/or efficiency of development solutions. Within the World Bank’s lending portfolio, these innovations involve new ways of designing or implementing projects that go beyond incremental improvements. Scaled operational innovations (e.g. e-procurement) and institutional innovations (e.g., public-private partnerships, or PPPs) often require systems change. The most effective examples in these categories combine three elements: (i) small initial pilot tranches designed to test feasibility in a controlled setting (e.g., a limited number of districts or a specific sector); (ii) real-time beneficiary feedback mechanisms that enable troubleshooting (e.g., citizen scorecards or SMS-based progress updates); and (iii) flexible design that allows adjustments without triggering full project restructuring. Projects that skipped the pilot-learn-adapt cycle and instead adopted rigid, multi-component blueprints were far more likely to stall, particularly in volatile or low-capacity settings.

Lesson: Successful operational and institutional innovations require structured flexibility in the project’s architecture, which allows course-correction without causing bureaucratic delays.

Technological innovations center on the development or adaptation of new technologies to solve development challenges. At the Bank Group, many of these innovations are driven by external research and general-use technologies that are adopted and adapted to improve efficiency in new sectors or geographies (e.g., enabling faster processing, remote service delivery, or richer data collection). Not surprisingly, the overall context affects both the level of sophistication and success of technological innovations. Projects in middle-income settings, or that paired new ICT with training, reliable connectivity, and strong user ownership, often showcased technology as a flagship achievement. In contrast, where the enablers were weak, especially in FCV contexts, over-engineered systems stalled or were abandoned while adaptive and “fit-for-purpose” tools were more successful.

Lesson: Technological complexity should align with local implementation capacity, and adequate operations and maintenance resources need to be secured at appraisal. Without these preconditions, otherwise promising innovations can become liabilities during implementation.

Collaborative innovations bring together diverse actors, including governments, the private sector, civil society, academia, and communities, to jointly address complex development challenges. These collaborations often take the form of self-help groups, multi-stakeholder coalitions, social entrepreneurship, and community-driven solutions. By leveraging collective resources, expertise, and perspectives, collaborative innovations achieve outcomes that isolated efforts often cannot. Projects that embed innovative ways of including beneficiaries or local civil society in design and delivery saw higher uptake and durability, especially in FCV settings. Key drivers included early trust-building, clearly defined partner roles, and sustained capacity support. Without them, even technically sound innovations lose traction. Collaborative innovations are often add-ons that act as multipliers for early-stage innovations, turning them into scalable, locally owned solutions.

Lessons: Projects with embedded collaboration—especially beneficiary or civil society involvement—show greater uptake and sustainability of their innovations. Sectors lacking collaboration levers would benefit from the experiences of other sectors.

Financial innovations advance the creation and dissemination of new financial products, services, technologies, or processes that improve or transform financial transactions and services. Innovations like digital payment systems, mobile banking, community funds, or microfinance enhanced the efficiency, accessibility, affordability, and functionality of financial markets and services, particularly to better serve underserved populations and address development challenges.

Financial innovation remains a frontier area in the WBG portfolio. Its success relies on governance and capacity; weak oversight or misaligned incentives quickly erode the benefits of novel financing structures. Financial innovations can de-risk projects by linking funding to results, involving local stakeholders, expanding access to finance, improving transparency, and fostering financial inclusion. However, explicit de-risking instruments—e.g. output-based disbursements, community grant windows, microfinance, mobile banking—surface in only ten percent of projects. Where governance and incentive frameworks are sound, these tools deliver outsized payoffs, signaling an underused opportunity for creative financing across various sectors. In FCVs, light but well-defined institutional setups (e.g., third-party agencies) have proved effective where full-scale reforms were unrealistic.

Lessons: Financial innovations perform best when supported by strong governance and well-aligned incentives. De-risking tools, such as output-based financing and community grant mechanisms, remain underused but show high impact when applied effectively.

Innovation types may overlap – the prevailing configuration includes institutional and operational innovations, followed by technology (Tables 3.5 and 3.6). Many High and Moderate innovation intensity projects deploy digital platforms with phased pilots, adaptive M&E, and other execution-focused adjustments—underscoring that ICT relies on the learning‐oriented delivery architecture. Financial innovations also create opportunities for cross-sectoral innovations, helping to refine incentive structures, strengthen risk mitigation, and support adaptive delivery mechanisms that ultimately attract greater and more effective private investment. For example, a project in Rwanda used a partial credit guarantee to leverage private bond markets for small and medium enterprise financing.

# Table 3.5. Prevalence of Innovation Types in the Innovation Portfolio

| Innovation Type | High + Moderate Innovative Projects | High + Moderate Innovative Projects (%) |
| --- | --- | --- |
| Operational/Institutional | 781 | 80% |
| Technological | 467 | 48% |
| Collaborative | 291 | 30% |
| Financial | 286 | 29% |

Note: The table refers to innovation types in 974 High + Moderate innovation projects. The innovation types are not mutually exclusive; many projects combine two or more.

Over the past three decades, the World Bank’s innovation portfolio has broadened across operational/ institutional, technological, collaborative, and financial areas, though with distinct trajectories. Operational and institutional innovations dominated in the late 1990s and 2000s, and they continue to provide the backbone of the portfolio. Technological innovations, initially limited, gained momentum during 2008–2017 and continued expanding  after 2018, becoming a defining feature of many innovative projects. Collaborative innovations grew steadily during the first two decades but have plateaued more recently, suggesting that while partnerships and co-creation remain important, they have not expanded at the same pace as other innovation types. Financial innovations followed a slower path: relatively modest in earlier cohorts, they gained traction only in the most recent decade, often in tandem with technology-driven approaches and reflecting the increased use of results-based financing, guarantees, and blended finance instruments. Taken together, these trends indicate that technology has become a central driver of innovation, financial instruments are beginning to follow a similar expansion curve, and collaboration remains steady but no longer the main growth frontier.

# Table 3.6. Prevalence of Innovation Types by Decade

| Innovation Type | 1998-2007 | 2008-2017 | 2018-2025 | Total |
| --- | --- | --- | --- | --- |
| Operational/Institutional | 168 | 289 | 324 | 781 |
| Technological | 104 | 172 | 191 | 467 |
| Collaborative | 65 | 113 | 113 | 291 |
| Financial | 53 | 90 | 143 | 286 |

Note: The table refers to innovation types in 974 High + Moderate innovation projects. The time period 2018–2025 is a partial cohort, with many projects still under implementation.

## Innovation Patterns in Different Geographies

Regional patterns of innovation intensity show limited variation. Projects ranking High and Moderate on the Innovation Index range from a high of 16.7 percent of projects in East Asia and Pacific and 15 percent in South Asia to a low of 9.2 percent in Europe and Central Asia (Table 3.7). In most other regions, about 11 to 13 percent of projects are innovative.

# Table 3.7. Innovation Intensity by Region

| World Bank Region | All Projects | High + Moderate Innovative Projects | % of Region Portfolio |
| --- | --- | --- | --- |
| East Asia and Pacific | 1213 | 203 | 16.7% |
| South Asia | 856 | 128 | 15.0% |
| Latin America and the Caribbean | 1412 | 185 | 13.1% |
| Eastern and Southern Africa | 1051 | 137 | 13.0% |
| Western and Central Africa | 1137 | 134 | 11.8% |
| Middle East and North Africa | 560 | 64 | 11.4% |
| Europe and Central Asia | 1289 | 119 | 9.2% |
| Other | 56 | 4 | 7.1% |

Note: The Other/Regional category covers projects not anchored in a single country. The majority are regional initiatives—especially in Africa, such as the West Africa Power Pool, Lake Chad Program, or Eastern Africa transport corridors—while a smaller share are global or multi-regional programs, such as climate funds, open data platforms, or pandemic instruments.

# Figure 3.1. Innovation Intensity by Region and Cohort

Note: The time period 2018–2025 is a partial cohort, with many projects still under implementation.

Innovation has a relatively even geographic spread across the regions. One might expect differences between regions with lower and higher capacity: strong institutions, better technology penetration, and skilled implementation partners provide an easier foundation. However, the data does not show a difference in innovation intensity in the World Bank portfolio for higher-capacity regions. For example, Europe and Central Asia, which includes many middle-income countries with relatively strong capacity, has the lowest percentage of innovative projects at 9.2 percent. Eastern and Southern Africa has a higher share of innovative projects at 13 percent. In lower-capacity regions, pressing development challenges can spur innovative solutions, such as using mobile technology to leapfrog infrastructure gaps.

Innovation intensity has increased in all regions over time, but the rate of increase varies across regions (Figure 3.1). Most regions experienced a similar increase in innovation intensity (4-6%) between the late 1990s and mid-2000s. Western and Central Africa and Latin America and Caribbean are a slight exception, with relatively higher increases of 7-8 percent during this earlier period. Since the mid-2000s, East Asia and the Pacific stands out with a 10 percent increase in innovation intensity between the 2008-2017 cohort and the 2018-2025 cohort. South Asia also experienced strong growth of 8 percent during this period, while Europe and Central Asia and Eastern and Southern Africa experienced more moderate increases of 7 percent. Meanwhile, innovation intensity plateaued in Middle East and North Africa, Western and Central Africa, and Latin America and Caribbean during the most recent period, with increases of only 1 to 3 percent.

## Innovation Patterns in Different Settings

We also compared innovation implemented in IDA and IBRD settings to understand what internal capabilities are required to adapt innovations for clients in these contexts. Figure 3.2 and the following section discuss key factors for success, such as aligning complexity with capacity, fostering local ownership, building partnerships, and using adaptive delivery.

# Figure 3.2. Innovation Factors in IDA and IBRD Settings

| IDA Context | IBRD Context |
| --- | --- |
| - Development urgency stimulates creative solutions to pressing challenges. - Adaptation and localization of global best practices require innovative approaches. - External support from donors and nongovernmental organizations (NGOs) catalyzes innovation and knowledge exchange. - Constraints (limited resources, weak governance) often drive novel, cost-effective solutions and partnerships. - Political will and reform-minded leadership can compensate for broader capacity gaps. | - Technology saturation and path dependency may drive preference for incremental improvements over disruptive innovations. - The lack of trust funds limits support options for early pilots and experimentation, and lower supervision budgets for lending operations limit the supervision capacity during scale-up. - High-capacity clients might engage other partners, such as private sector and academia, in innovative activities. |

#### Innovation in the IDA Context

In IDA projects, innovation often focuses on service delivery adaptations and optimization to compensate for low resource availability and capacity. Because government systems may be weak, projects innovate by involving local partners (NGOs, communities, or private providers) to achieve results. For example, when conventional methods struggled in a low-income country education project, the team piloted an alternative contracting mechanism through NGOs to deliver textbooks. Frugal innovations—for example, using mobile phones for data collection instead of costly surveys or training local paraprofessionals to extend services—succeed when they are tailored to limited resources and skills. A nutrition project highlighted an early warning system and small-scale livelihood micro-projects as key innovations but also indicated those components could have had greater impact with better institutional arrangements.

Local capacity building and community ownership are repeatedly stressed as critical enablers for innovations in the IDA context. A food security project in an IDA country found that a participatory approach was essential to build local capacity for an innovative idea. In such low-capacity environments, innovations must often be paired with capacity building, and staff must have skills in facilitation and training, not just technical design.

#### Innovation in the IBRD Context

IBRD projects often pursue more technically complex innovations that embed frontier technology. They can assume a baseline of capacity to handle sophisticated interventions. However, even in IBRD settings, innovations can falter if they are too complex.  For example, Argentina’s Native Forests & Protected Areas Project (approved in 1997, closed in 2007) integrated then-frontier tools, such as satellite imagery, aerial photography, LiDAR, and remote monitoring devices, to complement traditional biodiversity surveys and strengthen conservation management, supported by a blended IBRD–GEF financing package. While Argentina had the capacity to attempt the advanced approaches, the project found that some monitoring systems generated poor-quality data and that experimental land-use and buffer-zone livelihood pilots delivered mixed results and were difficult to replicate at scale.

#### Adaptation in Fragile and Conflict-Affected Situations

In fragile and conflict-affected situations (FCS), internal innovation capacity is both crucial and more difficult to deploy. Only 10.3 percent of FCS projects have High or Moderate innovation content versus 13.8 percent in non-FCS projects (Table 3.8). This gap could be due to low implementation capacity, data and information gaps, shifts in the WBG’s focus on FCV settings over time, and the reluctance of the Bank Group to include risky innovation activities in projects that already have a high risk rating and operate in fragile and low-resource environments. An alternative explanation is that FCS projects focus on delivering basic services through well-tested models and that process innovations (e.g. implementation arrangements, financing) are more common than project design innovations in FCS contexts. Additional research is needed to explore this hypothesis.

# Table 3.8. Innovation in FCS Contexts

| Portfolio Slice | High + Moderate Innovative Projects | Total Projects | Share High + Moderate Innovative Projects (%) |
| --- | --- | --- | --- |
| FCS | 204 | 1985 | 10.3% |
| Non-FCS | 770 | 5589 | 13.8% |

Note: Projects were tagged as FCS or Non-FCS based on the World Bank’s FCS list, which is updated annually (see https://www.worldbank.org/en/topic/fragilityconflictviolence/brief/classification-of-fragile-and-conflict-affected-situations). Projects are coded as FCS if the country was ever on the World Bank FCS list between FY15-FY25. This provides a consistent static classification across the full portfolio. Future analysis could explore other approaches to FCS classification and disaggregation into conflict versus fragility subsets.

## Innovation Patterns in Different Sectors

Clear sectoral patterns emerge in innovation intensity of the portfolio, with limited spillovers across sectors. Table 3.9 shows GPs like Agriculture, Environment, Health, and Digital have the highest share of projects with High + Moderate innovation intensity. These often involve technological and operational innovations, such as introducing new crop varieties or novel service delivery methods, reflecting active experimentation in service delivery and community engagement. Infrastructure-related practices (Urban, Water, Transport, Energy) show moderate innovation incidence, often tied to engineering or financial innovations like new contracting models or PPPs. In contrast, practices like Macroeconomics and Governance seldom explicitly mention innovation in evaluations, possibly because their operations use more traditional approaches or different language to describe change. Notably, the Finance, Competitiveness and Innovation GP, which by mandate includes support to private sector innovation, has only 9 percent of projects that are innovative. Thus, there might be a potential disconnect in learning capture, where innovative activities occur but are not explicitly documented as “innovations” in evaluation reports, possibly due to lack of a common definition or emphasis in reporting.

# 3.9. Sectoral Patterns of Innovation in GPs

| GP | All Projects | High + Moderate Innovative Projects | % of Sectoral Portfolio |
| --- | --- | --- | --- |
| Agriculture and Food | 483 | 113 | 23.4% |
| Environment | 538 | 98 | 18.2% |
| Health, Nutrition and Population | 540 | 94 | 17.4% |
| Digital Development | 24 | 4 | 16.7% |
| Urban, Resilience and Land | 902 | 138 | 15.3% |
| Water | 563 | 86 | 15.3% |
| Social Sustainability and Inclusion | 28 | 4 | 14.3% |
| Transport | 696 | 94 | 13.5% |
| Social Protection and Jobs | 419 | 53 | 12.6% |
| Education | 672 | 82 | 12.2% |
| Energy and Extractives | 622 | 75 | 12.1% |
| Finance, Competitiveness and Innovation | 586 | 52 | 8.9% |
| Poverty and Equity | 38 | 3 | 7.9% |
| Governance | 518 | 39 | 7.5% |
| Macroeconomics, Trade and Investment | 790 | 25 | 3.2% |

Note: Sectors with very low representation (below 1 percent of total sectoral portfolio) are not shown in this table and in the following analyses, as their small sample sizes do not allow for meaningful interpretation.

Innovations tend to remain siloed within certain sectors and GPs, though some have diffused across regions when knowledge-sharing mechanisms function effectively (Box 3.1). For instance, innovative financing schemes (like output-based aid or catastrophe bonds) might appear in only one practice’s projects and not mentioned elsewhere. Several evaluations lament limited cross-sector fertilization, saying that the World Bank needs to share global and cross-sectoral experience more productively on common challenges. The lack of a systematic process for transferring lessons means diffusion can be person-dependent or serendipitous.

Sectoral innovation patterns have also shifted across GPs over time (Figure 3.3). Overall, between 1998-2007 and today, the share of innovative projects has accelerated most significantly in Social Protection and Jobs (+25 percentage points) and Agriculture and Food (+19 pp). Looking specifically at the period between 1998–2007 and 2008–2017, Agriculture and Food shows the strongest early jump in innovation (+15 pp), followed by notable increases in Environment (+9 pp) and Social Protection and Jobs (+8 pp). Meanwhile, the second period between 2008–2017 and 2018–2025 is driven most strongly by Social Protection and Jobs (+17 pp), with Urban, Resilience and Land (+9 pp), Health, Nutrition and Population (+7 pp), Energy (+6 pp) and Transport (+6 pp) showing more moderate but still meaningful gains. Overall, the pattern suggests that most sectors have experienced rising shares of innovative projects over time alongside the broader global increase, but that a smaller set of GPs, particularly Social Protection and Jobs and Agriculture and Food, account for a disproportionate share of the observed increase in innovation intensity across cohorts.

# Figure 3.3. Sectoral Patterns of Innovation Across GPs by Cohort

Note: The time period 2018–2025 is a partial cohort, with many projects still under implementation.

Box 3.1. Assessment of the Bank Group’s Internal Innovation Capacity

Has the Bank Group’s internal innovation capacity matured or remained fragmented? Evidence suggests a bit of both.

Innovation is no longer a fringe activity. It is discussed by senior management, supported by dedicated funding (e.g., IDA PSW, trust funds for innovation in FCV), and many staff have experience with novel approaches.

However, silos and uneven implementation persist. Certain GPs have robust systems to vet and mainstream innovations, while others do not. Moreover, innovation initiatives have experienced turnover, for example, the “Innovation Lab” and specific incubators. Often these programs operate for only a few years before they are rebranded or absorbed, resulting in lost momentum. This discontinuity contributes to perceptions of fragmentation among staff.

## Technology Premium

Digital innovations have become widespread in the Bank Group portfolio, routinely embedded in projects and often in combination with operational, financial, or collaborative innovations. Their presence is no longer limited to a small subset of highly and moderately innovative projects but is increasingly visible across practices. However, the impact of these technologies on performance varies by context. Outcome ratings show a slight negative “technology premium” in Low innovation projects (–0.04), while high and moderate innovation projects record a small but positive premium (+0.07) (Table 3.11). This pattern suggests that digital tools are most effective when layered onto already-innovative project designs that have adaptive structures, robust operational processes, and strong collaborative arrangements. Without these enabling conditions, the addition of technology alone does not yield better outcomes, underscoring that digital features serve as accelerators for well-structured innovations, rather than as substitutes for it.

# Table 3.11. Technology Premium Across Projects

| Innovation Tier | Mean Outcome (No Technology) | Mean Outcome (Technology) | Technology Premium |
| --- | --- | --- | --- |
| High + Moderate Innovative Projects | 4.14 | 4.21 | 0.07 |
| Low Innovation | 4.03 | 4.00 | -0.03 |

The sectoral analysis of the technology premium shows clear variation across GPs (Table 3.12). The strongest gain is in Water, followed by MTI, , Governance, and Poverty and Equity.. In contrast, Agriculture, Environment, and FCI show negative premiums. This suggests that technology can lift outcomes where it complements strong delivery systems and adaptive designs, while in other sectors it either adds little or introduces complexity that dampens effectiveness. Overall, the evidence underscores that digital features work best as enablers within well-structured innovations, rather than as standalone solutions.

# Table 3.12. Technology Premium in Projects by GP (High + Moderate Projects)

| GP | Mean Outcome (No Technology) | Mean Outcome (Technology) | Raw Technology Premium |
| --- | --- | --- | --- |
| Digital Development |  | 3.50 |  |
| Agriculture and Food | 4.41 | 3.98 | -0.43 |
| Environment | 4.30 | 3.98 | -0.32 |
| Finance, Competitiveness and Innovation (FCI) | 4.05 | 3.92 | -0.13 |
| Energy and Extractives | 4.16 | 4.23 | 0.07 |
| Social Protection and Jobs | 4.46 | 4.60 | 0.14 |
| Urban, Resilience and Land | 4.08 | 4.25 | 0.16 |
| Transport | 4.26 | 4.44 | 0.17 |
| Education | 3.98 | 4.18 | 0.20 |
| Health, Nutrition and Population | 4.06 | 4.32 | 0.26 |
| Social Sustainability and Inclusion | 4.00 | 4.33 | 0.33 |
| Poverty and Equity | 4.50 | 5.00 | 0.50 |
| Governance | 3.38 | 3.90 | 0.53 |
| Macroeconomics, Trade and Investment (MTI) | 3.30 | 4.07 | 0.77 |
| Water | 3.75 | 4.63 | 0.88 |

Note: Sector-level estimates of the technology premium should be interpreted with caution. In several GPs—notably Governance, Finance, and Energy—the number of technology-tagged projects is relatively small, so a few high- or low-rated operations can substantially influence the averages. Observed differences therefore reflect descriptive patterns rather than robust statistical effects.

## IFC Collaboration and Innovation Patterns

International Finance Corporation (IFC) collaboration remains relatively rare within the Bank Group portfolio. Of the 7,574 projects reviewed, only 59 (less than 1 percent) mention IFC in their lessons. Among these, 20 projects are classified as High or Moderate innovation, while 39 are classified as Low (Table 3.13). This suggests that while IFC engagement is not widespread, when it does occur it is more likely to be associated with innovation: about 2 percent of High/Moderate projects mention IFC compared to only 0.6 percent of Low projects.

# Table 3.13. Projects with IFC Collaboration

| IFC Mention in Lessons | High + Moderate Innovation Projects | Low Innovation Projects | Total |
| --- | --- | --- | --- |
| No IFC Mention | 954 | 6561 | 7515 |
| With IFC Mention | 20 | 39 | 59 |
| Total | 974 | 6600 | 7574 |

Note: The overall numbers of IFC collaboration might be higher because some collaborations might not have been reflected in the ICRR lessons and/or might not be linked to innovative approaches.

Due to the small size of the IFC-linked subset in the portfolio, the authors complemented the quantitative review with an LLM-assisted analysis to identify patterns across key dimensions (Table 3.14). The findings show that projects involving IFC tend to be disproportionately innovative but also operate in more complex contexts, which may explain why their average outcomes are slightly lower than the rest of the portfolio. Sectorally, these projects cluster in the Infrastructure, Sustainable Development, and Equitable Growth, Finance, and Institutions practices. Country mentions point to a mix of IDA and IBRD markets (e.g., Cameroon, Chad, Indonesia, Pakistan), underscoring IFC’s reach across both emerging and fragile environments. Lessons consistently emphasize innovation levers—technology-enabled design, phased operational approaches, financial risk-sharing, and multi-stakeholder collaboration. These align closely with the World Bank’s recent institutional reforms, including the Procurement Framework (2016), ESF (2018), MFD, and PSW, which aimed to lower barriers to innovation and private sector engagement.

# Table 3.14. Profile of Bank Group Projects with IFC Investment

| Metric | Insight |
| --- | --- |
| Portfolio footprint | 59 projects of 7,574 (≈0.78%) reference IFC in lessons—rare but present across decades. This is a broader set than strict “mobilization,” capturing advisory, co-design, or parallel IFC activity alongside World Bank operations. |
| Innovation intensity | 20of 59 projects (34%) are High + Moderate on the Innovation Index, about three times the portfolio average (12.9%). IFC-linked World Bank projects tend to include more innovation, even if the total number is small. |
| Outcome quality (IEG Outcome) | Average outcome (numeric 1–6) is 3.98 for IFC-mention projects vs. 4.04 for non-IFC projects. The IFC-linked set skews to more complex contexts and sectors; the enrichment for innovation does not automatically translate into higher mean ratings in this broad cut. |
| Top sectors (GPs) | Highly concentrated where private solutions are intrinsic: Finance, Competitiveness and Innovation (20), Energy and Extractives (12), followed by Macroeconomics/Trade (9), Urban, Resilience, and Land (4), Environment (3), Social Protection and Jobs (3), and Agriculture (3). The pattern aligns with areas that have bankable revenue models or policy and investment interfaces. |
| Regional spread (proxy by country mentions) | The most frequent country mentions among IFC-linked World Bank projects include: Indonesia Vietnam, India, Pakistan, Cameroon, Bangladesh, Cote d’Ivoire, and Chad. This represents a mix of markets where IFC operates actively and policy and investment reforms intersect. The full region split requires lending-group/region fields. |
| Innovation levers observed | Recurrent features in lessons include (i) technology-heavy design (digital platforms/fintech/smart meters); (ii) operational agility (phased pilots, programmatic scale); (iii) financial novelty (guarantees, PPP/output-based results-based blends, risk-sharing); (iv) multi-stakeholder collaboration (public–private–regulator triads). These levers map to Bank Group reforms that lower transaction costs for testing and scaling, such as the new Procurement Framework (2016), ESF (2018), MPA (2017), MFD/Cascade, and IDA-PSW. |

## Private Capital Mobilization

Private capital mobilization (PCM) is often more associated with innovative operations than with the average project. Table 3.15 compares the prevalence of PCM language across two portfolio slices. In the full set of 7,574 ICRRs, 10.4 percent contain at least one reference to mobilizing private finance. Within the 974 operations that the Innovation Index classifies as High or Moderate, the count rises to 33.6 percent. PCM references are about3.2 times more common among the World Bank’s more innovative projects than in the portfolio at large.

# Table 3.15. PCM Projects

| Portfolio slice | Projects mentioning PCM | Share of portfolio slice |
| --- | --- | --- |
| All Projects | 788 | 10.4% |
| High + Moderate Innovative Projects | 327 | 33.6% |

PCM is most prominent in sectors with favorable regulatory frameworks and market opportunities. Sectors traditionally dominated by market-based solutions, such as digital, energy, and transport, represent a higher percentage of private investment (Table 3.16).

# Table 3.16. Sectors with Active PCM

| GP | Total Projects | PCM Projects | % with PCM |
| --- | --- | --- | --- |
| Digital Development | 24 | 9 | 37.5% |
| Transport | 696 | 105 | 15.1% |
| Energy and Extractives | 622 | 91 | 14.6% |
| Health, Nutrition and Population | 540 | 71 | 13.1% |
| Finance, Competitiveness and Innovation | 586 | 67 | 11.4% |

## Role of Donors and Trust Funds in Innovation

Partners finance higher-risk pilots, bring in external ideas and technical knowledge, and can help institutionalize successful innovations in client countries. Many projects with High or Moderate innovation content benefited from such support, indicating that the World Bank often leverages partner resources to push the innovation frontier. Bilateral donors and foundations in particular emerged as key sources of knowledge through trust funds, while UN agencies and partners contributed primarily through collaborative implementation.

Projects with trust fund backing often reported positive innovation outcomes, including slightly better success rates for pilots and strong examples of sustained impact. These findings show the potential upside of well-managed partnerships. At the same time, the findings highlight that trust fund governance matters: trust fund and partner support can catalyze lasting change, but it is not automatic. Fragmentation and parallel processes can reduce efficiency and hinder learning, echoing the teams’  observations that poorly coordinated funds increase transaction costs and complicate ownership. Bank Group projects and borrowers achieve the best results if multiple donors and ideas are unified, that is, they employ the “coupled” model of innovation when both bottom-up and top-down approaches are used in a single case. The positive cases show that embedded partner expertise and funding help create institutions, skills, and policies that outlive the project (for example, new financing mechanisms, regulations, or ongoing programs). Many innovations successfully piloted with trust fund support were subsequently scaled through financing by governments or other donors, fulfilling the trust funds’ intended role.

Trust funds are most effective as a bridge to local ownership, not a substitute for it. When used strategically—with flexible funding and knowledge transfer—trust funds and partners have proven to be powerful drivers of innovation in Bank Group lending. However, when projects treat trust funds as standalone, add-on components, the innovation often lacks a champion after the project closes. The challenge and opportunity ahead is to replicate these conditions consistently, ensuring that external resources truly enhance learning and scaling rather than create silos. The evidence suggests that with the right approach, trust-funded innovation can achieve both high performance and sustainable development impact.

# Lessons from the Portfolio Analysis

## Key Drivers of Performance in Innovative Projects

Projects with High or Moderate innovation content, on average, are associated with better performance outcomes. For example, innovative projects outperform the average IEG outcome rating by 0.13 points (3.2%) while Low innovation projects underperform the average IEG outcome rating by 0.02 points (-0.5%) (Figure 4.1, Table D.1). Innovative projects also receive higher ratings in quality at entry, supervision, and overall World Bank performance (Tables D.2b-d). This correlation between innovation, quality supervision, and performance warrants additional research: strong outcomes may result from effective innovations, and well-performing teams might be more inclined to try and document innovations.

# Figure 4.1. Average IEG Project Ratings by Innovation Intensity

However, innovation is not the sole driver of success; rather, it tends to flourish under the enabling conditions of well-managed projects (see Appendix E). This positive correlation suggests that innovation is compatible with—and may enhance—results at scale. While innovative projects can carry risks, the analytics indicate the rewards often outweigh the risks when innovations are implemented thoughtfully. Moreover, the positive trend in outcomes could also reflect that innovative projects foster a culture of learning and problem-solving that benefits implementation.

Controlled and disciplined experimentation is the primary driver of successful innovations. Among High + Moderate innovation projects, nearly half explicitly reference piloting and/or scaling (Table 4.1) This confirms that “learning while doing” is a dominant feature of innovative operations, though the depth of piloting discipline varies.

Rigid project designs and a failure to adapt during implementation reduce the effectiveness of innovations. For instance, in Chad, a public works project attempted a new implementation agency model but did not adjust its design after pilot difficulties, ultimately leading to failure. Standard M&E is often too high-level to capture results from innovations, and process evaluation and rapid evaluation methods are underutilized. Overreliance on Randomized Controlled Trials can delay the adaptation and uptake of promising innovations.

Innovation design is a careful balancing act: innovations must be ambitious enough to drive meaningful change, yet flexible enough to respond to challenges. When this balance is struck, innovation becomes a positive force that improves project outcomes rather than undermines them. Innovations are not inherently beneficial by default: their success depends on embedding structured flexibility into project design to enable timely course corrections. Poorly designed or rigid innovations—such as skipping early pilot testing or locking into complex, multi-component plans—can damage the entire project, leading to stalled progress or failure. Innovation always carries risks, so when it is badly executed, it can be worse than maintaining the status quo. To mitigate this, innovations should be piloted on a small scale, incorporate real-time feedback, and maintain flexible mechanisms for adjustment without requiring full project restructuring.

The fit-for-purpose approach to innovations leads to higher success rates, especially in FCS where the design often must be simplified and adjusted to local context. One portfolio review found that projects in FCS that tried complex designs struggled, whereas those with a narrow focus and clear, simple innovation performed better, such as cash-for-work programs using mobile payments. Flexibility is paramount. Internally, this requires streamlined procedures (e.g., fast-track approvals, simplified procurement) and empowered field teams to make decisions. In one FCS lesson, independent verification agents maintained oversight in insecure areas, which enabled the project to experiment with community grants while satisfying fiduciary standards.

Innovation risks are amplified in FCS. Fragility and conflict contexts may give the sense that the “risk budget” is already exhausted, leaving little space for innovation. Yet high-performing innovation projects embed de-risking measures that include integrating innovative pilots into larger components, using gradual iterations from local or sector-specific pilots to systemwide changes, and developing local engagement and capacity.

## Contextual and Participatory Drivers of Innovation

Without contextualization, even well-designed innovations can struggle to gain traction and fail to scale. Among the innovative projects in the dataset, only 26 percent mentioned piloting in the local context and explicit scale-up and 21 percent mentioned piloting or adaptation to the local context but no scale-up (Table 4.1). The majority of projects (53%) did not mention adaptation or piloting. When adaptation is embedded—whether through pilots, demonstration models, or phased rollouts—projects are better able to align ambition with country absorptive capacity. Successful examples illustrate this balance:

- In Egypt, a water management project localized NASA-developed tools to national institutions, demonstrating the value of coupling global expertise with local capacity.

- In Angola, an education project tested a demonstration model before expanding capacity building for scale-up, which is critical in a low-capacity, post-conflict context.

- In Bangladesh, irrigation projects began with flexible small-scale pilots that could be adapted iteratively, ensuring farmer involvement and local relevance.

- In fragile settings, pilots remain especially valuable as feasibility tests. In the Republic of Congo, a community-driven development (CDD) pilot confirmed that communities could manage funds even in a conflict context; its success later informed a national rollout and inspired replication by other donors.

# Table 4.1. Importance of Context-Appropriate Innovation

| High + Moderate Innovation Projects | Definition | Projects | Portfolio Share |
| --- | --- | --- | --- |
| Pilot + Scaled | Lessons mention both piloting in the local context and explicit scale-up or replication | 254 | 26.0% |
| Pilot Only | Piloting or adaptation language but no scale-up cues | 203 | 21.0% |
| No Pilot | No adaptation or pilot wording | 517 | 53.0% |

Note: The pilot and scale tags are derived from keyword searches in project lessons and are not exhaustive; some piloting or scaling features may not be explicitly captured in the evaluation text. In addition, the full dictionary of innovative terms is broader than the subset applied here, and projects can be classified as High + Moderate innovation even when no pilot or scaling language appears. These categories therefore provide indicative rather than comprehensive coverage of piloting and scaling practices in the High + Moderate portfolio.

Participatory approaches to innovation—involving communities and stakeholders in the design and piloting of new solutions—have been shown to create ownership and build capacity at the community level thereby anchoring innovations in the local context. Qualitative evidence from project lessons underscores the value of early and structured engagement with IFC, especially in project design and risk assessment. Overall, adaptive, inclusive practices have been crucial for scaling innovations, especially in low-capacity settings.

In FCS, innovative projects often rely on unorthodox partnerships, such as working through local NGOs, faith-based organizations, or informal community structures, due to weak government capacity. Building trust is also a critical component; in conflict-affected settings, introducing a new approach requires careful stakeholder consultation to gain buy-in and ensure do-no-harm. Several FCS project lessons highlight the role of strong facilitation to align government actors, community leaders, and donors around an innovative approach.

Internal drivers of innovation include visionary and supportive leadership and empowered and stable task teams. Project lessons regularly highlight the key role of leadership and high-quality staffing, importance of managers’ and TTLs’ willingness to take risks on an unproven approach, and the openness of local staff to new ideas as decisive elements for success. Effective cross-unit collaboration and knowledge exchange have enabled replication (e.g., a trade information portal, new community-driven models) across countries and regions.

However, significant constraints persist. These include entrenched risk aversion, bureaucratic fragmentation, capacity gaps, overly complex project designs, lack of continuity in scaling innovations, and insufficient incentives for reflection and adaptation (Table 4.2). In FCS in particular, excessive caution further limits innovation.

# Table 4.2. Bank Group Enablers vs. Constraints on Innovation

| Aspect | Enablers | Constraints |
| --- | --- | --- |
| Leadership | Strong leadership at all levels; champions set vision and protect teams during failures. | Risk-averse culture penalizes failure; fear of career implications; conservative management. |
| Culture and Incentives | Culture of experimentation; creativity and bold thinking are encouraged and recognized. | Fear of failure; rigid rules and red tape; lack of incentives for learning and adaptation. |
| Knowledge Sharing and Learning | Effective knowledge systems; expert panels and peer review; communities of practice and peer learning networks. | Fragmented knowledge flows; lack of coordination; insufficient time or incentives for reflection. |
| Collaboration and Cross-Unit Teams | Cross-disciplinary collaboration; new instruments (e.g., MPA) and co-financing mechanisms promote integrated innovation. | Bureaucratic fragmentation; siloed departments foster competition rather than cooperation. |
| Team Stability and Skills | Stable, multi-disciplinary teams with diverse skills enable cumulative learning and creativity. | High staff turnover; skills gaps; capacity constraints on M&E and technical areas (e.g., digital tools, AI). |
| Adaptive Processes | Flexible project designs allow for adjustments, contingencies, and agile processes. | Overly complex or rigid project designs; slow approval processes; inflexible bureaucracy (e.g., procurement and legal processes). |
| Client Ownership and Demand | Strong borrower commitment cultivated by proactive World Bank staff engagement. | Lack of client awareness or buy-in; insufficient support for local capacity building. |
| Continuity and Follow-Through | Sustained management support and programmatic approaches enable scaling and mainstreaming of successful innovations. | Abrupt shifts in priorities; lack of -up mechanisms; innovations remain isolated pilots. |
| Context-Specific Risks (FCS) | Initiatives like the Turn Around Allocation and simplified procedures encourage responsible risk-taking. | Excessive caution in fragile contexts due to fears over security, fiduciary, and reputational risks. |

Note: Based on the review, there is an order of importance and interdependency between these enablers and constraints. The most important enablers are (i) leadership, (ii) incentives, (iii) knowledge-sharing and collaboration, (iv) team and skills, (v) adaptive processes, and (vi) client ownership. Key constraints are (i) risk aversion culture, (ii) complex processes, internal silos and bureaucracy, (iii) team turnover and lack of continuity, and (iv) insufficient capacity or M&E for learning.

## Institutional and External Drivers of Innovation

Among the key factors enabling innovation, leadership support and risk culture stand out as the most impactful. When leadership and culture align positively, other barriers tend to be more easily overcome. Leadership frequently emerges as a prevalent theme in project lessons, with many attributing success or failure to the presence or absence of a champion or an enabling manager. For example, leadership can mitigate bureaucracy, such as when a strong country director waives some processes to allow an innovation pilot. Conversely, issues like over-complexity and capacity mismatches are commonly noted in unsatisfactory projects, making them significant inhibitors to success.

Though the WBG has numerous examples of successful innovation adoption, diffusion across the institution is uneven. For example, a World Bank education team noted that certain community-based school construction methods kept reappearing independently in multiple countries, prompting a call for more shared learning in the donor community to avoid duplicating existing solutions. Effective diffusion tends to occur in areas with formal networks (such as sector groups, communities of practice, global solutions groups) or programs (like South-South knowledge exchanges, Gender Labs, DIME) that transfer knowledge across boundaries. Without these deliberate efforts, many promising innovations risk unnecessary redundancy or reinvention in isolation or remain confined to the enthusiastic unit that originated them.

While significant progress has been made in piloting and scaling up innovations, the rapid pace of global technological change demands an even more agile and accelerating innovation cycle. Tracing innovation spillovers reveals moving from pilot to implementation can take 10–15 years to achieve scale-up and mainstreaming (Appendix D). Many innovative projects’ lessons mention delays due to rigid processes, insufficient capacity, or slow institutional learning. To fully reap the benefits of ongoing technological transformation—such as digital platforms, data-driven solutions, and new delivery models—the WBG must further streamline its innovation pipeline, invest in capacity building, and foster a culture that encourages experimentation and rapid course correction. Accelerating the innovation cycle will enable the WBG and its clients to stay ahead of emerging challenges, leverage cutting-edge solutions, and achieve greater, more sustainable development outcomes at scale.

## D. Looking Ahead: Fostering Strategic and Scalable Innovation

Going forward, these lessons encourage the WBG and development practitioners to continue embracing innovation, boldly but intelligently. Over time, the WBG has moved from sporadic, personality-driven innovation to a more programmatic, strategic approach. Each generation of projects builds on the last, and the trajectory is clear: when implemented in an inclusive and context-aware manner, innovation is a powerful driver of lasting development impact. The internal toolkit for managing innovation has expanded, with instruments for piloting, funding mechanisms, and learning platforms. Yet, the transformation remains incomplete, as the culture and systems are still catching up to fully integrate innovation into the Bank Group’s institutional fabric.

The challenge ahead for the WBG is to avoid complacency. As “innovation” becomes a buzzword, there is a risk that every project will claim it without truly doing things differently. Maintaining a sharp focus on actual innovative practice and results will be key in the next phase. This means staying on the cutting edge by mobilizing technology, new partnerships, and financing tools, while also heeding the hard-won lessons of execution and context. By doing so, the Bank Group can leverage innovations to accelerate development outcomes, even in the most challenging environments, as long as it remains committed to learning and adapting. As the data shows, this is exactly what has been happening over the past three decades of project experience.

# Data Gaps and Future Research Directions

To deepen understanding of how innovation operates within the WBG, several areas merit further research—ranging from operational design choices and staff experiences to cross-institutional comparisons and longitudinal case studies. Table 5.1 presents a set of potential additional metrics for capturing information about innovations, detailing the type of data each metric collects and guidance on how to calculate them effectively.

- Bringing innovation insights closer to operations: The authors’ analysis suggests that innovative projects often correlate with stronger outcome ratings. However, more descriptive and systematic work is needed to understand how and why this occurs. Future studies could identify specific design and implementation choices that enable TTLs to successfully embed innovation in projects. This includes whether innovation is better introduced as a component or subcomponent, how project appraisal documents can support mid-course adjustment when an innovation proves ineffective, and what mechanisms promote flexibility without adding undue complexity.

- Understanding staff perceptions: While the lessons dataset provides an evaluative perspective, it lacks direct data on staff experiences with internal innovation processes. Complementary analysis, such as staff surveys or interviews, could help identify perceived bottlenecks in the World Bank’s systems and gather suggestions to overcome them. This type of research, perhaps by the World Bank’s Human Resources or an internal committee, could reveal cultural and procedural inhibitors not evident in written lessons.

- Examining innovation in IFC and comparing it to other institutions: This study focuses on IBRD/IDA projects, but a fuller understanding of the Bank Group’s innovation capacity requires examining IFC’s portfolio as well. IFC has its own innovation initiatives, and a cross-institutional comparison could yield important lessons. For example, potential research could contrast IFC’s greater operational agility with IBRD’s more process-intensive approach, and identify how each institution might learn from the other. Where data allow, an extended analysis could trace patterns of project-level innovation within IFC, offering a more complete picture of how innovation is fostered across the Bank Group.

- Undertaking longitudinal case studies: The quantitative trend analysis shows macro patterns, but detailed case studies of specific innovation mechanisms over time would enrich understanding. For instance, tracing the evolution of LILs used by the World Bank from the 1990s to the present could provide a narrative of institutional learning—revealing how innovations spread, what role internal champions played, and how lessons were shared.

- Exploring context-specific innovation case studies: The current analysis applies a consistent definition of innovation across the portfolio to enable comparability at scale. However, what “innovation” means and how it is expressed in project narratives may vary by context and theme. In FCV settings, for example, where operations often prioritize the delivery of basic services under severe constraints, there may be less emphasis on novelty in project designs or interventions and more emphasis on innovative processes (e.g. implementation or financing arrangements). Future work could therefore explore a set of targeted “edge” case studies to refine our understanding of innovation and to strengthen how innovation is defined, detected, and interpreted across different operating environments.

- Additional data sources and methods: Future research could broaden both the evidence base and the analytic approach by drawing on complementary data sources that capture innovation earlier in the project cycle and outside the IEG lessons corpus. Within the WBG, this could include data from the Analytical and Advisory Services (ASA), Trust Fund proposals and progress reports or lending project appraisal and supervision documentation. Methodologically, future iterations could also strengthen detection and classification of innovation by incorporating additional parameters of keyword frequency and synonymity for sensitivity analysis, and combining and cross-validating the current approach with semantic methods, such as embedding-based similarity, to reduce reliance on a fixed dictionary and better surface innovation (Lewis et al. 2020; Reimers and Gurevych 2019).

# Table 5.1. Potential Additional Metrics for Capturing Information About Innovations

| Metric | What It Captures | How to Calculate from the IEG Lessons or Project Records |
| --- | --- | --- |
| Innovation Density | Overall prevalence of innovations | Number of projects whose lessons include at least one type of innovation (based on the Oslo Manual classification) ÷ by total projects in snapshot year or period |
| Novelty Mix Index | Balance between incremental vs. radical innovations | Weighted score calculated by assigning values of 1 to ‘new to organization,’ 2 to ‘new to target beneficiaries,’ and 3 to ‘new to world’ innovations; scores are summed per project and averaged across the portfolio |
| Conversion Ratio | Effectiveness of turning ideas into funded pilots, drawn from Innovation Value Chain framework (Hansen & Birkinshaw 2007) | Number of pilots implemented ÷ by distinct innovative ideas recorded in design or appraisal documents |
| Diffusion Ratio | Success in scaling pilots, drawn from Innovation Value Chain framework (Hansen & Birkinshaw 2007) | Number of innovative pilots subsequently replicated or expanded ÷ by pilots implemented |
| Cross-Unit Collaboration Rate | Extent of silo-breaking | Projects with two or more Vice Presidential Units or regions listed as TTLs or co-implementers ÷ by total innovative projects |
| Evidence Rigor Distribution | Quality of proof behind innovations | % of innovative projects at each Nesta Innovation Level (1–5) |
| Risk-Adjusted Success Rate | Willingness to attempt and tolerance of failure | (Innovative pilots rated Satisfactory or higher minus those rated Unsatisfactory) ÷ by total innovative pilots; report the share of failed pilots to understand the level of risk involved |
| Time-to-Majority Adoption | Speed of uptake among target stakeholders, drawn from diffusion of innovations theory (Rogers 2003) | Median months from pilot launch to >50% adoption within the beneficiary group, averaged over all projects with reliable adoption time-series |

# Conclusion

This study demonstrated the value of combining GenAI, advanced data analytics, and human expertise to extract actionable insights from large-scale evaluation data. By integrating computational text mining with expert validation, the analysis established a replicable framework for measuring “innovation intensity” and tracing how innovations evolve, diffuse, and influence outcomes over time. This approach not only enhances the WBG’s capacity to learn from its own portfolio but also provides a model for evidence-based innovation management in development institutions.

The portfolio evidence affirms that innovation contributes positively to development outcomes when it is context-aware, disciplined, and adaptive. High-performing innovations share several traits: they start small through structured pilots, incorporate real-time feedback, and scale only after local capacity and institutional fit are secured. Operational and institutional innovations—such as e-procurement, programmatic approaches, and results-based financing—proved most resilient, while technological innovations achieved lasting results when paired with strong delivery systems and user ownership. Collaborative and participatory models further increased uptake and sustainability, particularly in fragile and low-capacity settings where community engagement substituted for weak institutions.

The data also highlight key enablers: visionary leadership, empowered and stable teams, flexible procedures, and knowledge systems that support cross-sector learning. Where these were present, innovation flourished; where bureaucratic rigidity, risk aversion, or fragmented knowledge flows persisted, promising ideas stalled. Donor partnerships and trust funds were most effective when used as bridges to local ownership rather than stand-alone experiments, and IFC collaboration amplified technological and financial innovation through private-sector leverage.

The challenge ahead is to sustain that progress of embedding innovation as a continuous institutional function rather than an episodic initiative. This will require maintaining rigorous learning loops, protecting space for experimentation, and ensuring that “innovation” remains tied to measurable improvements in outcomes. In doing so, the WBG can continue to transform its accumulated project experience into a living system of adaptive solutions—demonstrating not only that innovation works, but why and under what conditions it delivers lasting development impact.

The findings of this paper suggest that, for the World Bank Group, creating a portfolio of adaptive and well-managed innovations supported by strong leadership and a culture that fosters experimentation is essential for achieving sustained development impact. Programs that invest in team skills, knowledge sharing, and flexible operational processes can help mainstream innovation and improve project performance across diverse contexts. More broadly, the evidence points to important implications for development practice beyond the WBG: enabling innovation at scale requires institutional commitment to learning, robust monitoring and evaluation, and mechanisms that support local ownership and iterative adaptation. By prioritizing these enabling conditions, development organizations and governments can accelerate the diffusion and sustainability of innovative solutions, ultimately driving more effective and resilient outcomes for communities worldwide.

# Bibliography

Barker, Pierre, Amy Reid, and Michael Schall. 2015. “A Framework for Scaling up Health Interventions: Lessons from Large-Scale Improvement Initiatives in Africa.” Implementation Science.

Bason, Christian. 2018. Leading Public Sector Innovation: Co-Creating for a Better Society. Bristol: Policy Press.

Borins, Sandford. 2014. The Persistence of Innovation in Government. Washington, DC: Brookings Institution Press.

Bruno, A., et al. 2019. “Public Sector Innovation: A Systematic Review.” Public Management Review 21 (3): 307–331.

Cooley, Laurence, and Johannes F. Linn. 2014. Scaling Up—From Vision to Large-Scale Change: A Management Framework for Practitioners. Washington, DC: Brookings Institution.

Crossan, Mary M., and Marina Apaydin. 2010. “A Multi-Dimensional Framework of Organizational Innovation: A Systematic Review of the Literature.” Journal of Management Studies 47 (6): 1154–1191.

Damanpour, Fariborz, and Dalhia Aravind. 2012. “Managerial Innovation: Conceptions, Processes, and Antecedents.” Management and Organization Review 8 (2): 423–454.

Farnese, Maria Luisa, et al. 2019. “Learning-Oriented Leadership and Innovative Work Behavior: The Mediating Role of Knowledge Sharing.” Journal of Workplace Learning 31 (3): 181–198.

Hartley, Jean. 2005. “Innovation in Governance and Public Services: Past and Present.” Public Money & Management 25 (1): 27–34.

Hansen, Morten T., and Julian Birkinshaw. 2007. “The Innovation Value Chain.” Harvard Business Review 85 (6): 121–130.

Kattel, Rainer, and Mariana Mazzucato. 2018. “Mission-Oriented Innovation Policy and Dynamic Capabilities in the Public Sector.” Industrial and Corporate Change 27 (5): 787–801.

Lewis, M., et al. 2020. “Beyond Dictionaries: Semantic Approaches for Text Mining.” Journal of Computational Social Science.

Linn, Johannes F. 2012. “Scaling Up in Agriculture, Rural Development, and Nutrition.” IFPRI Discussion Paper.

Nesta. 2019. Standards of Evidence for Impact. London: Nesta.

OECD. 2017. The Innovation Imperative in the Public Sector. Paris: OECD Publishing.

OECD/Eurostat. 2018. Oslo Manual: Guidelines for Collecting, Reporting and Using Data on Innovation. Paris: OECD Publishing.

O’Reilly, Charles A., and Michael L. Tushman. 2013. “Organizational Ambidexterity: Past, Present, and Future.” Academy of Management Perspectives 27 (4): 324–338.

Ramalingam, Ben, et al. 2014. “Bringing Adaptive Management to Development Practice.” ODI Working Paper.

Reimers, N., and I. Gurevych. 2019. “Sentence-BERT: Sentence Embeddings Using Siamese BERT-Networks.” EMNLP Proceedings.

Rogers, Everett M. 2003. Diffusion of Innovations. 5th ed. New York: Free Press.

Schut, Marc, et al. 2020. “Scaling Agricultural Innovations: A Framework for Analysis.” Agricultural Systems.

Woltering, L., et al. 2019. “Scaling—From ‘Reach and Adoption’ to ‘System Change.’” Agricultural Systems.

# Appendix A. Detailed Steps in the Workflow

| # | Description of the Step | Primary Tool(s) Used |
| --- | --- | --- |
| 1 | Normalize the evaluation corpus: Load the IEG corpus of project evaluations (ICRRs and PPARs). Standardize GPs, regions, dates, and ratings (map outcomes to numeric values). Implement de-duplication rules (prefer PPAR over ICRR, or else keep the most recent ICRR). Fix text encoding artifacts in the Lessons Learned text, and drop projects with empty lessons. Recode FCS status to include any country on the World Bank Harmonized FCS country list at any point between FY15 and FY25. The result is a “one project, one record” table with the Lessons Learned text as the main unstructured field for mining. This approach yielded a clean, analysis-ready database of 7,574 projects from a total of 8,569 evaluations. | Python |
| 2 | Develop an innovation keyword dictionary: Ask two LLMs to generate lists of innovation-related terms, drawing on their knowledge of innovation practice and international development. Combine the two lists, remove duplicates, and review the resulting pool by the expert authors to remove irrelevant, ambiguous, or overly generic terms. Refine further using Python notebooks to inspect matched snippets in context and add morphological variants. The final innovation keyword dictionary of 165 terms is provided in Appendix B. | GenAI + expert human review + Python |
| 3 | Tag each project by innovation content: Scan each Lessons Learned text using the innovation keyword dictionary and count distinct hits per project (do not repeat the count of the same token within a document). | Python |
| 4 | Classify projects by innovation intensity and construct the Innovation Index: Use a threshold-based classification system: High innovation = 4 or more distinct keyword hits, Moderate innovation = 2–3 distinct keyword hits, Low innovation = 0 or 1 distinct keyword hit. Store both the raw hit count and the tier so sensitivity checks can vary thresholds ±1. | Python |
| 5 | Human validation: Draw a sample of High and Moderate projects (random, purposive, and targeted borderline cases); have two reviewers independently assess innovation presence and whether the automated tier assignment is appropriate. Resolve disagreements through discussion. | Expert human review |
| 6 | Build the “innovative subset”: Classify projects as High + Moderate innovations to form the subset for taxonomy analyses and diffusion work. Use the full corpus for denominators or comparisons when needed (e.g., to assess technology premiums, PCM insights). | Python |
| 7 | Develop the innovation taxonomy: Use LLMs to generate tagging keywords for each of the four innovation categories (operational/institutional, technological, collaborative, and financial). Apply these keywords via Python to produce provisional category assignments across all projects, defaulting to operational/institutional where no category is matched and allowing multi-label assignments where supported. Apply a similar Python-assisted inspection procedure as in Step 2 to check for potential mismatches. Review a sample of assignments (random, purposive, and targeted borderline cases) against the Lessons Learned text; revise as needed. | GenAI + expert human review + Python |
| 8 | Conduct iterative human–model reasoning: Engage LLMs as interlocutors to explore pattern candidates (through dozens of prompts), propose alternative framings and cuts by time, GP, instrument, and FCV. Researchers steer prompts, filter noise, and anchor interpretations in Bank Group context and history. | GenAI + expert human input |
| 9 | Formulate hypotheses: Distill the co-interpreted ideas into testable hypotheses about innovation’s distribution, correlates, and performance implications. Examples include “the technology premium is positive conditional on adaptive delivery”; “operational innovations dominate across decades”; and “IFC references are associated with higher innovation intensity”. Record hypothesized mechanisms and observable proxies for further testing. Authors screen and retain only hypotheses that are internally coherent, observable in the dataset, and feasible to operationalize. | GenAI + expert human review |
| 10 | Operationalize each hypothesis: For each hypothesis, define measurable indicators and keyword expansions (e.g., pilot/scale lexicon, IFC/PCM lexicon, technology markers). These lexicons enable consistent text mining across hypotheses. The list of keyword expansions is available upon request. | GenAI |
| 11 | Apply feature tagging: Using the new lexicons, run targeted keyword matching scans to identify references to pilots, scale‑up, technology, IFC, PCM, and so on. Attach boolean flags to each project. | Python |
| 12 | Analyze the portfolio: Produce a time series analysis (such as five-year cohorts); conduct regional/GP breakouts; compare FCS vs. non-FCS; and generate cross-tabulations by innovation tier to identify distributional patterns. | Python |
| 13 | Assess performance associations (technology or innovation premium): Calculate mean differences in ratings by innovation tier (the innovation premium) and by technology presence within tiers and by GP (the technology premium), across outcome, bank performance, quality at entry, and quality of supervision ratings. | Python |
| 14 | Identify top innovation model candidates: Prompt LLMs to surface candidate innovation models prevalent across the portfolio (e.g., e-procurement, PPPs, CDD, digital government); authors review and refine the final list, retaining only models that are conceptually distinct, plausibly prevalent in the portfolio, and feasible to operationalize with keywords. | GenAI + expert human review |
| 15 | Generate model keyword dictionaries and count mentions: Use LLMs to generate keyword lists for each candidate model identified in Step 14. Apply Python binary keyword matching to flag each project for each model's presence, then count and compare model prevalence across the portfolio. | GenAI + expert human review + Python |
| 16 | Contextualize the narrative: After generating tables and figures, prompt LLMs to propose institutional interpretations (e.g., links to procurement reform, ESF, GP reorganization). Manually verify this against data and known milestones. Add sensitivity notes when inferences hinge on tagging breadth. | GenAI + expert editing |
| 17 | Synthesize and report results: Integrate quantitative outputs and curated exemplars into a coherent narrative. Ensure all figures carry sensitivity notes. | Expert synthesis |

# Appendix B. Innovation Keyword Dictionary

The keyword list includes every root token or phrase that was explicitly loaded into the text scanner as a positive innovation cue, and therefore drove the assignment of projects to High, Moderate, or Low innovation tiers. This vocabulary captures seven thematic dimensions:

- Innovation

innovative, innovation, innovations, novel, novelty, breakthrough, cutting-edge, frontier, transformative, disruptive, experimental, quasiexperimental, frugal-innovation, good-enough tech, reverse-innovation

- Innovation cycle

experimentation, prototype, prototyping, pilot, pilots, piloted, piloting, sandbox, proof-of-concept, demo, demonstration, demonstrations, demonstration model, trial, trials, beta rollout, phased rollout, phased scale-up, scale-up, scaled-up, scaling, scaling-up, replicate, replicated, replication, mainstream, mainstreamed, mainstreaming, leapfrog, market test, scaling-readiness, innovation-ecosystem

- Results-based management and learning

adaptive, adaptively, adaptive management, learning-by-doing, feedback loop, real-time M&E, agile, agile iteration, pivot, course-correct, A/B test, randomized trial, RCT, results-based, rapid-assessment, pulse survey, early-warning, adaptive logframe, flexible-design, learning agenda

- Specific innovation types

outcome-based, output-based, performance-based, pay-for-results, PforR, results-based financing, output-based aid, blended finance, blended-financing, catalytic fund, guarantee, guarantees, guaranteed, risk-sharing, viability-gap, PPP, public-private-partnership, concession, concessions, private-capital, mobilise private, leverage private, fintech, mobile money, mobile banking, digital payment, e-wallet

- Enabling technologies

blockchain, distributed-ledger, big data, data-analytics, AI, artificial-intelligence, machine-learning, predictive model, drone, remote-sensing, satellite imagery, GIS, geo-mapping, e-government, e-service, e-procurement, e-bidding, electronic procurement, digital platform, cloud-based, open-data, API, interoperability, telemedicine, e-health, e-learning, EdTech, online curriculum, virtual classroom, chatbot, IVR, SMS-based

- Innovation-enabling processes

crowd-funding, crowdsourcing, crowd-sourced, living lab, innovation-challenge, prize competition, accelerator, incubator, venture fund, co-design, co-creation, citizen science, citizen-feedback, social audit, scorecard, scorecards, grievance-redress, community-driven, community-managed, self-help group, participatory-planning, stakeholder platform, multi-stakeholder, knowledge-exchange, South-South exchange, cross-sector, cross-sectoral, cross-regional, integrated approach, systems approach

- Public-good innovations

climate-smart, low-carbon, nature-based, circular economy, gender-lens, youth-led, inclusive-innovation, last-mile delivery, social enterprise

# Appendix C. Select Hypotheses Tested

This appendix presents a representative set of hypotheses tested during the analysis. The list is not exhaustive; additional hypotheses were explored as part of the broader research process.

Innovation contributes to higher project success – validated.

Hypothesis: Projects that incorporate explicit innovative approaches (e.g., new technologies, pilot methodologies, and partnerships) achieve higher outcome ratings on average.

Validation: Categorize projects according to the presence of innovation-related keywords or themes in their documents and statistically compare them using their IEG outcome ratings. A regression analysis could be performed, with outcome rating as the dependent variable and indicators for various innovation types as independent variables, controlling for region, sector, project size, and so on.

The innovation premium varies by sector – partially validated

Hypothesis: The return to innovation varies across GPs. Larger positive effects are expected where innovations complement frontline service delivery (e.g., water, education, governance) and smaller or negative effects are expected where added complexity can dominate (e.g., agriculture, environment), echoing the sectoral technology premium patterns already observed.

Validation: Interact the Innovation Index with GP indicators and innovation types (technological, operational/institutional, collaborative, financial) to estimate marginal effects specific to GPs. The technology premium cuts could also be replicated at the GP level. As a sensitivity check, the sample could be restricted to projects with a single dominant innovation type to reduce multi-label collinearity and then re-estimated to exclude those GPs with small sample sizes.

Adaptive and collaborative innovations improve performance in fragile contexts – validated

Hypothesis: In FCS, projects that employ adaptive design (e.g., pilots, flexible components) and collaborative approaches (e.g., community participation, NGO partnerships) are expected to achieve better results than those that follow standard methods.

Validation: Subset the data to FCS projects and examine those that mention such innovations have higher success rates or better implementation scores. Keyword mapping could be used to flag FCS project documents for terms related to adaptive or collaborative strategies; subsequently compare their average outcomes to other FCS projects. Another method is a case-comparison: qualitatively compare a set of successful FCV projects that used innovative approaches against unsuccessful projects that did not use them to see if a pattern emerges. This can be aided by text analysis or coded lessons.

Innovation yields benefits in FCS, but context shapes the premium – not validated

Hypothesis: Even when adopted, innovations yield smaller performance gains in FCS than in nonFCS portfolios due to capability, fiduciary, and access constraints. The FCS share of innovative projects is also lower than in nonFCS, indicating a harder diffusion path.

Validation: Estimate a model of Outcome ~ High/Moderate Innovation + FCS + High/Moderate Innovation × FCS + controls, where the interaction term tests whether the innovation premium is attenuated in fragile contexts. As a sensitivity check, the analysis could be disaggregated by innovation type (e.g., operational/institutional vs. technological innovations) to assess whether certain approaches work more effectively in fragile portfolios. Parallel estimates conducted by decade could show whether any attenuation narrows over time, potentially reflecting the cumulative effect of institutional reforms.

Strong project management enables innovation (and vice versa) – partially validated

Hypothesis: A positive feedback loop occurs between innovation and project implementation quality: teams that manage projects well (high Quality at Entry, effective supervision, strong M&E) will implement innovations successfully, which in turn leads to better outcomes.

Validation: The data hints at this correlation. More rigorous testing could involve a multivariate analysis wherein the presence of innovation is predicted by quality ratings, or conversely, outcome success is predicted by an interaction between innovation and quality measures. For example, a logistic regression could model the probability of a project being rated successful (Moderately Satisfactory or higher) as a function of the inclusion of innovative elements alongside Quality at Entry and supervision ratings. Significant interaction terms would indicate that the combination of innovation plus strong management boosts project success. In addition, clustering or factor analysis might reveal an “innovation and excellence” factor.

Different types of innovations have different impacts – not tested

Hypothesis: Not all innovations are equal. Perhaps technological innovations show the biggest gains in certain sectors, whereas social or financial innovations matter more in others. For example, maybe technological innovation correlates strongly with success in middle-income countries but not in low-income ones, whereas community innovation correlates with success in rural poverty projects.

Validation: Test sub-hypotheses by segmenting the data: run separate analyses for technology-focused projects vs. others or by GP. A sentiment analysis or topic modeling on the lessons could identify whether a “technology” topic emerges and aligns with higher outcomes in one subset, while a “participation” topic aligns in another. This analysis would require natural language processing techniques to classify lessons as innovation types, followed by statistical comparisons across these categories.

Diffusion speed accelerates with institutional reforms – partially validated

Hypothesis: Major Bank Group corporate reforms (e.g., Procurement Framework 2016, MPA 2017, ESF 2018) coincide with the step-changes in innovation diffusion, accelerating uptake across multiple GPs.

Validation: Compare innovation density before and after reform periods using a defined significance threshold (e.g., a minimum share of projects exceeding the innovation cut-off) and model mentions by decade. Event-study specifications could be run in ±5-year windows around reform enactments to assess timing effects and parallel trends.

IFC collaboration is an innovation multiplier – partially validated

Hypothesis: Projects with IFC collaboration are disproportionately represented among High and Moderate innovation projects and more likely to deploy financial and technological innovations.

Validation: Compare innovation intensity (share of High/Moderate projects) and the distribution of innovation types between IFC-mention projects and the rest of the portfolio, controlling for sector and region. Given the small sample size, exact tests could be used and confidence intervals reported transparently. As an exploratory extension, the interaction of the IFC-mention with financial or technological tags could be tested to assess whether such projects are more likely to adopt or diffuse these innovations, rather than simply achieve higher mean outcome ratings.

Stronger diffusion correlates with better development outcomes – partially validated

Hypothesis: Bank Group projects that successfully scale or widely adopt their innovations (i.e., high diffusion) achieve higher outcome ratings and sustained development impacts. The intuition is that full adoption of an innovation (rather than remaining in the pilot stage) likely means it was successful and generated significant benefits, which would be captured in IEG outcome ratings or long-term results.

Validation: Identify projects in the dataset where the innovative component was scaled or replicated, information that can be flagged through IEG lessons or project documents. Compare these projects’ outcome ratings to those where innovation remained limited. If available, ex-post impact measures could be incorporated, that is, whether certain indicators improved more in scaled cases. For a more quantitative test, a logistic regression model could be applied, using outcome rating or a success dummy as the dependent variable and a diffusion dummy (scaled vs. not scaled) as the independent variable, controlling for other relevant factors like project size or sector. If the hypothesis holds, the regression would show a statistically significant positive association between diffusion and project success. This would confirm that when innovations diffuse, the development impact is larger and more appreciable—somewhat intuitive but worth evidentiary confirmation.

Innovations in multiple countries diffuse more rapidly in subsequent adopters due to learning effects – not tested

Hypothesis: Once an innovation has been piloted in an initial set of places, subsequent adopters are able to implement it more quickly and with greater efficiency due to accumulated institutional learning and knowledge transfer.

Validation: Examine a sequence of countries that adopted the same innovation, for example, an education reform piloted in Country A and subsequently introduced in Countries B and C. Comparative assessments of project timelines and results could help determine whether later adopters achieved results within shorter timeframes than earlier ones, and whether preparation times shortened as toolkits or diagnostics became available. Where outcome trajectories are available, the analysis could test whether the adoption curve in later countries appears steeper, suggesting that knowledge transfer contributed to accelerate uptake. Such evidence would support the view that cross-country learning and South-South exchanges can serve as catalytic drivers of innovative diffusion, enabling lagging countries to progress more quickly from early adoption to majority uptake.

# Appendix D. Evolution of Innovation Practices at the World Bank Group

Over the past three decades, the Bank Group has moved from treating innovation as a series of ad hoc project features to viewing it as a more deliberate capability embedded in operations. Table D.1 shows the full distribution of the innovation tiers in the dataset.By linking project-level innovation classifications with outcome ratings over time, it is possible to quantify an “innovation premium” and assess whether the Bank’s growing emphasis on innovation has translated into stronger development results (Table D.2a-d).

# Table D.1. Distribution of Innovation in WBG portfolio

| Innovation tier | Total Projects | Share of total projects (%) |
| --- | --- | --- |
| Low | 6600 | 87.1% |
| Moderate | 774 | 10.2% |
| High | 200 | 2.6% |

The “innovation premium” refers to the performance gain associated with projects that explicitly incorporate innovative features in their design and implementation. In practice, this means that projects classified as having high or moderate via the Innovation Index tend to achieve slightly better outcome ratings than the portfolio average, while low-innovation projects perform at or below the portfolio baseline. These findings can provide empirical support for investing in experimentation, learning, and adaptive designs: even relatively small gains at the project level compound across a large portfolio and over time.

# Table D.2a. Innovation Premium Across Projects -

| Projects | Average Rating | Difference from Overall | % Difference |
| --- | --- | --- | --- |
| All | 4.04 | - | - |
| High + Moderate Innovative Projects | 4.17 | 0.13 | 3.2% |
| Low Innovation | 4.02 | -0.02 | -0.5% |

# Table D.2b. Innovation Premium Across Projects – Bank Performance Rating

| Projects | Average Rating | Difference from Overall | % Difference |
| --- | --- | --- | --- |
| All | 4.13 | - | - |
| High + Moderate Innovative Projects | 4.2 | 0.07 | 1.7% |
| Low Innovation | 4.12 | -0.01 | -0.2% |

# Table D.2c. Innovation Premium Across Projects – Quality of Supervision Rating

| Projects | Average Rating | Difference from Overall | % Difference |
| --- | --- | --- | --- |
| All | 4.34 | - | - |
| High + Moderate Innovative | 4.43 | 0.09 | 2.1% |
| Low Innovation | 4.32 | -0.02 | -0.5% |

# Table D.2d. Innovation Premium Across Projects – Quality at Entry Rating

| Projects | Average Rating | Difference from Overall | % Difference |
| --- | --- | --- | --- |
| All | 4.02 | - | - |
| High + Moderate Innovative | 4.12 | 0.1 | 2.5% |
| Low Innovation | 4.01 | -0.01 | -0.2% |

The Bank Group’s approach to innovation has evolved considerably from the 1990s to the 2020s. Examining project evaluations over time shows distinct shifts in strategic emphasis and innovation management mechanisms.

1990s: Innovation was not a prominent buzzword in the early 1990s. Projects then were often narrower in design, focusing on infrastructure, adjustment lending, and so on. Lessons rarely used the term “innovation.” When innovations occurred, they were usually pilot projects or new policy experiments spurred by visionary task managers. By the end of the 1990s, innovation mentions increased slightly, partly due to the introduction of new lending instruments like APL that encouraged phased innovation and learning.

Early 2000s: During the 2000s, the World Bank began to more explicitly recognize innovation, especially as knowledge-sharing initiatives grew, such as communities of practice or the Development Marketplace. More lessons reference “innovative approaches,” often in human development and rural projects where participatory methods were tried. The strategic approach was still not uniform, and innovation was somewhat ad hoc. However, there was a rise in pilot programs and an emphasis on scaling up successful pilots in strategies. By the mid-2000s, knowledge management was formalizing: the World Development Report 2004: Making Services Work for Poor People, encouraged innovation in service delivery, and the World Bank’s ICT investments grew.

Late 2000s to early 2010s: A notable shift happened in the late 2000s into the 2010s, coinciding with a broader push for aid effectiveness and results. Terms like “innovation” and “experimentation” started to appear in sector strategies. For instance, the climate change agenda and the establishment of the Climate Investment Funds in 2008 injected a spirit of innovation, piloting renewable energy models and other sustainable initiatives. The authors’ analysis shows an increase in innovation mentions occurring around 2010, possibly reflecting these trends: about 10–12 percent of projects in 2009–2011 mention innovation, up from about 5 percent a few years earlier. During this period, management mechanisms also evolved, with the World Bank introducing tools like Innovation Labs and competitive innovation awards internally, signaling top-down encouragement. Additionally, projects more frequently had built-in learning or adaptive components (e.g., additional financing windows, phased rollouts), showing a strategic move toward more flexibility. However, this period also saw some fragmentation; each region or practice might launch its own innovation initiative (e.g., there are references to “innovation funds” in regional Vice Presidential Units), not always coordinated across the World Bank.

Mid to late 2010s: By the mid-2010s, innovation became a part of the mainstream discourse. The creation of the GPs (2014) was partly intended to break silos and spread innovative solutions globally. Cross-regional references rose in lessons as projects proudly noted they drew lessons from another country’s experience. Innovation types also diversified: digital development emerged as a GP, reflecting the central role of technological innovation. This period also emphasized collaboration and crowdsourcing, as the World Bank began partnering more with technology firms and universities and using open data. Internally, this meant task teams had more access to external ideas. By the late 2010s, IEG evaluations often assessed how well projects incorporated innovation and learning. The trend line peaks around 2018–2020, with about 12–15 percent of projects mentioning innovation. It is likely no coincidence that President Jim Yong Kim (2012–2019) strongly promoted innovation during this time, e.g., the Agile Bank initiative, encouraging simplification and experimentation. New financing instruments (e.g., PforR) and incubation programs for innovative projects emerged. The approach shifted toward scaling innovations, as many country strategies started to include objectives like “scale up successful pilots in X sector.”

Once the World Bank put systematic support around new ideas, innovative projects began to deliver consistently better development ratings (Figure D.1).

# Figure D.1. Innovation Premium Across Projects by Decade

2020s: In the early 2020s, the Bank Group’s innovation capacity faced new tests, which included responding to the COVID-19 pandemic and climate crises. Initial data for projects evaluated in 2021–2025 show innovation mentions at their highest proportion yet, at about 15 percent in 2023. This likely reflects how the World Bank had to innovate rapidly for the COVID-19 response through new virtual training and digital cash transfer programs, which IEG documented. The strategic approach was arguably more holistic—concepts like “adaptive learning,” “disruptive technology,” and “agile project design” were more common in corporate strategies. The institution had matured in recognizing innovation, and operational policies were adjusted. For example, the ESF (2018) allowed adaptive risk management, and the new Procurement Framework (2016) allowed innovative procurement methods, enabling more flexibility. However, some evaluations still describe the innovation ecosystem as fragmented, noting multiple initiatives but lacking coherence. For instance, an innovation piloted in one unit may not be known by other units due to information overload or lack of systematic knowledge capture.

Box D.1. Assessment of the Bank Group’s Internal Innovation Capacity

Has the Bank Group’s internal innovation capacity matured or remained fragmented? Evidence suggests a bit of both. Innovation is no longer a fringe activity. It is discussed by senior management, supported by dedicated funding (e.g., IDA PSW, trust funds for innovation in FCV), and many staff have experience with novel approaches. However, silos and uneven implementation persist. Certain GPs have robust systems to vet and mainstream innovations, while others do not. Moreover, innovation initiatives have experienced turnover, for example, the “Innovation Lab” and specific incubators. Often these programs operate for only a few years before they are rebranded or absorbed, resulting in lost momentum. This discontinuity contributes to perceptions of fragmentation among staff.

# Appendix E. Tracing the Diffusion of Innovation Models

The authors defined the innovation model as a proven, archetypal approach that embodies a distinctive method for addressing a development challenge through novel products, services, processes, or organizational practices (Table E.1). Such models can be adopted, adapted, replicated, and scaled across diverse contexts and geographies, enabling sustainable impact through iterations, contextualization, learning, optimization, and eventual mainstreaming. Examples include CDD, mobile banking, and e-procurement—each representing a replicable blueprint that leverages specific technologies, stakeholder engagement, and institutional arrangements to achieve transformative outcomes.

When an innovation scales up and disseminates, it appears repeatedly in ICRRs across countries and sectors. A single mention means that the initial pilot remained localized to a single project, even though it might have scaled up within its local context. Hundreds of mentions means that the innovation was integrated into mainstream operations. It is important to note, however, that this analysis is not comprehensive and will require further refinement, as some innovations may have been missed.

# Table E.1. Selected Examples of Innovation Models Generated Based on the Analytics

| Innovation Model | Total Mentions |
| --- | --- |
| Public-private partnership (PPP) | 271 |
| Community-driven development (CDD) | 150 |
| Conditional cash transfers (CCT) | 46 |
| Electronic procurement (e-procurement) | 34 |
| Remote sensing | 20 |
| Digital government platform/portal/services | 20 |
| Electronic learning (e-learning) | 15 |
| Mobile banking | 9 |
| Biometric ID | 4 |

Note: Innovation models surfaced through GenAI are drawn from the frequency and context in which certain models appear in IEG evaluation lessons. The method identifies models that are both recurrent and explicitly labeled as “innovative” in project documentation. As such, it may underrepresent innovations that were implemented but not described in this way, or that remain more context-specific or recent. The list should therefore be read as illustrative of the most visible and widely diffused models in the evaluation corpus, rather than an exhaustive catalogue of all innovative practices across the Bank Group portfolio.

Each of these innovation models originated as a pilot in the 1990s (Table E.2.), evolved into a working prototype and locally tested solution, and benefited from data collection and evaluations. Their replication was supported by institutional systems, including knowledge products, formal learning, and in some cases, mandates from corporate guidance or requests by multiple client governments. Their outsized share of representation, compared to the “long-tail” of innovations with only a few mentions, serves as quantitative evidence of spillover effects.

# Table E.2. Top Four Innovation Models by Decade

| Innovation Model | 1998-2007 | 2008-2017 | 2018-2025 |
| --- | --- | --- | --- |
| Public-private partnership (PPP) | 68 | 111 | 92 |
| Community-driven development (CDD) | 27 | 78 | 45 |
| Conditional cash transfers (CCT) | 0 | 17 | 29 |
| Electronic procurement (e-procurement) | 3 | 18 | 13 |

Note: The table highlights only the four innovation models with more than 100 tagged projects across the portfolio. Other models were excluded from in-depth analysis due to lower counts, pointing to more limited diffusion over time.

## Diffusion of Public-Private Partnership Model: Key Milestones and Evidence

Table E.5 shows how PPP language took off and then peaked in the mid-2000s. In the 1998–2007 decade, 54.4 percent of models were tagged as High or Moderate innovation. The prevalence decreased to 40.5 percent in 2008—2017 and remained steady at 42.4 percent in 2018—2025.

# Table E.5. Diffusion of PPP Model Over Time

| Evaluation decade | PPP model in All Projects | PPP model in High + Moderate Innovative Projects | Share framed as innovation (%) |
| --- | --- | --- | --- |
| 1998-2007 | 68 | 37 | 54.4% |
| 2008-2017 | 111 | 45 | 40.5% |
| 2018-2025 | 92 | 39 | 42.4% |

Note: The time period 2028–2025 is a partial cohort, with many projects still under implementation.

The World Bank’s first Build-Operate-Transfer toll road and power pilots in the early 1990s (e.g., P006040 Argentina Toll-Road Concessions, early independent power projects in East Asia) showed that private capital could finance and operate public infrastructure when supported by Bank guarantees. At the time, “PPP” language was still rare—ICRRs spoke of “Build-Operate-Transfer concessions” or “management contracts” rather than a repeatable model. Each bespoke deal contributed to an internal belief that crowding-in private finance could stretch limited IBRD/IDA envelopes.

Three corporate shifts triggered spillover: (i) the 2002 launch of PPIAF as upstream technical assistance; (ii) expansion of IBRD/Multilateral Investment Guarantee Agency (MIGA) guarantee products; and (iii) dedicated IFC advisory mandates. Projects like P070108 Uganda Bujagali and P083588 Vietnam Cai Mep-Thi Vai Port illustrate how regional teams replicated the model with only minor tailoring. Once the infrastructure playbook was standardized, PPP thinking migrated:

- P110267 Lesotho Queen ’Mamohato Hospital PPP proved private design-build-operate in a low-income setting.

- P131118 Turkey Health PPPs scaled the model to a €10 billion hospital program, backed by IBRD guarantees and MIGA political-risk cover.

- Small-ticket “micro-PPPs” such as P094613 Ghana OBA Rural Telecom cascaded into fragile states, helped by output-based-aid trust funds.

The decline reflects saturation: ICRRs now describe PPPs as baseline expectations for large-scale capital expenditures (CAPEX) or service-delivery reform rather than as cutting-edge experimentation. Current lessons emphasize climate-aligned blended finance PPPs (e.g., P163099 Uruguay Solar PV Guarantee), digital PPP auction platforms integrated with e-procurement portals (Philippines, Ukraine), and IDA PSW structures that derisk private CAPEX in FCV settings (e.g., P176389 Mozambique Temane Gas-to-Power). The World Bank’s 2020 PPP Framework codifies these advances, embedding climate and SDG alignment into procurement rules.

# Table E.6. Citations of Public-Private Partnership Arrangements Across the Bank Group Portfolio

| Cluster (Anchor Keywords) | Typical Wording in Lessons | Approximate Share of all PPP tags | Peak Decade(s) |
| --- | --- | --- | --- |
| Concessions / Leases (concession, concessions, lease, BOT) | “Design of concession frameworks required strong regulatory oversight.” “Long-term concession arrangements depended on credible tariff policies.” “Private operator performance improved under structured lease contracts.” | ~27% | 1998–2007 |
| PPP Framework / PPP Units (PPP, public-private-partnership, PPP unit, enabling framework) | “Establishing a dedicated PPP unit strengthened transaction preparation.” “A clear legal framework was critical to attract private investors.” “Institutional capacity constraints limited PPP rollout.” | ~26% | 2018–2025 |
| Guarantees / Risk-Sharing Instruments (guarantee, partial risk guarantee, risk allocation) | “Risk allocation between public and private partners was not adequately structured.” “Guarantee mechanisms enhanced investor confidence.” “Political risk mitigation was essential for project bankability.” | ~10% | 1998–2007 |
| Results-Based / Output-Based PPP Models (results-based, output-based, performance-based) | “Performance-based payments improved service delivery outcomes.” “Output-based aid mechanisms aligned incentives.” “Results-linked disbursement strengthened accountability.” | ~5% | 2018–2025 |

Note: Cluster shares and peak decades are LLM-generated and indicative rather than exact. They reflect qualitative patterns of PPP diffusion across project types, not precise statistical measures from the tagging exercise.

## Diffusion of CDD Model: Key Milestones and Evidence

Over time, the community-driven development (CDD) model has moved from a set of country-specific experiments to a widely used operational platform across regions and sectors. Early pilots demonstrated that communities could plan and implement local investments more effectively than centrally managed projects. Subsequent generations of operations adapted the model to different institutional and sectoral contexts, paired it with digital tools and climate-resilient investments, and increasingly framed CDD arrangements themselves as an innovation in service delivery and local governance.

The first large-scale demonstrations came from flagship operations such as Indonesia’s Kecamatan Development Program I (P039025) and Malawi’s Social Action Fund I (P001666). These projects showed that village committees could identify, contract, and maintain micro-infrastructure with lower leakage and faster delivery than comparable line-ministry projects. Positive IEG outcome ratings and rapid disbursement performance validated the basic CDD design and encouraged replication.

A second wave of programs—including the Philippines’ Kapit-Bisig Laban sa Kahirapan–Comprehensive and Integrated Delivery of Social Services (P077012), Sri Lanka’s Gemidiriya (P074872), and Afghanistan’s National Solidarity Program I (P082977)—helped establish CDD as a core instrument for local development and post-conflict reconstruction. In 2003, the World Bank issued a CDD Operational Guidance Note, which formalized CDD approaches globally. Most Regions subsequently appointed CDD focal points and created trust funds to finance training, technical support, and knowledge exchange.

As the model matured, sector operations in Water, Transport, and Social Protection began incorporating CDD components to finance feeder roads, water points, and cash-for-work programs, using community structures as implementation platforms rather than standalone projects. Examples include the Sierra Leone National Social Action Project (P079335), Nigeria Community and Social Development Project (P090644), and Haiti Reconstruction Fund’s community window (P130749).

Table E.10. Diffusion of CDD Model Over Time

| Evaluation decade | CDD model in All Projects | CDD model in High + Moderate Innovative Projects | Share framed as innovation |
| --- | --- | --- | --- |
| 1998-2007 | 27 | 8 | 29.6% |
| 2008-2017 | 78 | 29 | 37.2% |
| 2018-2025 | 45 | 19 | 42.2% |

Note: The time period 2028–2025 is a partial cohort, with many projects still under implementation.

More recent operations pair CDD with digital tools (mobile grievance apps, geo-tagged photos), climate-resilience menus and performance-based block grants. Mozambique Sustainable Rural Economy Project (P174002) tests “CDD-plus-value-chain” links, while DR Congo STEP-2 (P159217) combines e-procurement with community scorecards in conflict zones.

# Table E.11. Citations of CDD Arrangements

| Cluster (Anchor Keywords) | Typical Wording in Lessons | Approximate Share of all CDD tags | Peak Decade(s) |
| --- | --- | --- | --- |
| Community-Driven Development (Core CDD Model) (CDD, community-driven, community-driven-development, village fund, block grant) | “Community-driven approaches improved local ownership and accountability.” “Block grants empowered communities to prioritize their own investments.” “Strong facilitation was critical for effective CDD implementation.” | ~38% | 2008–2017 |
| Social Funds / Local Development Funds (social fund, local development fund, community fund, subproject financing) | “Social funds provided flexible financing for community infrastructure.” “Transparent subproject selection strengthened trust.” “Capacity building at local level was essential for sustainability.” | ~24% | 1998–2007 |
| Participatory Planning & Governance (participatory planning, local councils, village committees, decentralization) | “Participatory planning improved targeting and inclusion.” “Decentralized governance structures enhanced responsiveness.” “Local councils required sustained technical support.” | ~21% | 2008–2017 |
| Livelihoods & Inclusion Platforms (self-help groups, producer groups, livelihood grants, women’s groups) | “Self-help groups strengthened economic resilience.” “Targeting vulnerable households increased social inclusion.” “Group-based models fostered social capital.” | ~17% | 2018–2025 |

# Appendix F. Diffusion of Innovation Models in Fragile versus Non-Fragile Context

FCS are the most difficult environments in which to introduce, adapt, and scale innovation. Limited state capacity, fiduciary risks, weak infrastructure, and volatile political contexts substantially raise the costs of experimentation and slow the diffusion of successful models. Yet over the past three decades, several innovation models have gradually diffused into fragile settings (Table F.1). This evolution is less about rapid uptake and more about the cumulative impact of the World Bank’s successive reforms, instruments, and executive initiatives, which created openings for fragile clients to adopt tools initially established in more stable contexts.

# Table F.1. Diffusion of Innovation Models in FCS vs. Non-FCS

| Innovation Model | FCS Mentions | Non-FCS Mentions | Total Mentions |
| --- | --- | --- | --- |
| Public-private partnership (PPP) | 52 | 219 | 271 |
| Community-driven development (CDD) | 39 | 111 | 150 |
| Conditional cash transfers (CCT) | 11 | 35 | 46 |
| Electronic procurement (e-procurement) | 18 | 16 | 34 |

1998–2007: Innovation within Institutional Reform and Private Sector Expansion

During 1998–2007, innovation models diffused primarily within non-FCS contexts, reflecting the dominant WBG paradigm of the time: institutional reform, privatization, and public sector modernization in relatively stable environments. This was the era shaped by the post–Washington Consensus shift toward governance and institutional quality, following the 1997 World Development Report The State in a Changing World. PPPs scaled mainly in non-FCS countries (55 vs. 13 in FCS), consistent with efforts to crowd in private capital under stronger regulatory regimes. CDD was present but largely embedded in rural development and decentralization reforms rather than framed explicitly as a fragility tool. E-procurement and CCT were largely absent, reflecting limited digital infrastructure and the still-emerging global social protection architecture. Fragile states were not yet at the center of WBG strategy; innovation diffusion into FCS settings was therefore cautious and selective.

2008–2017: Fragility Turn, Governance Reform, and Institutionalized Innovation

The 2008–2017 period coincides with a structural pivot in WBG strategy toward fragility, risk management, and institutional resilience. Following the 2011 World Development Report on Conflict, Security and Development, fragility became a core institutional priority, and this is mirrored in the data. CDD expanded sharply in FCS (2 → 20 mentions), aligning with the emphasis on local governance, social cohesion, and community legitimacy in fragile environments. E-procurement’s surge in FCS (1 → 14) reflects heightened fiduciary controls and transparency mechanisms amid rising concerns about corruption and aid effectiveness. PPP diffusion also accelerated, supported by the “Maximizing Finance for Development” (MFD) agenda that emerged mid-decade, encouraging private capital mobilization even in riskier markets. Meanwhile, CCT emerged and began scaling, consistent with the global consolidation of social protection systems following the 2008 financial crisis. This decade represents institutionalization: innovation became embedded in operational doctrine, and fragile states were no longer peripheral but central to experimentation and scaling.

2018–2025: Human Capital, Digital Governance, and Context-Specific Specialization

The most recent period reflects strategic consolidation under frameworks such as the 2018 Fragility, Conflict, and Violence (FCV) Strategy, the Human Capital Project, and the Digital Development agenda. Diffusion patterns become more differentiated rather than uniformly expansionary. CDD remains concentrated in FCS settings, consistent with the FCV Strategy’s emphasis on social cohesion and localized institutional strengthening. E-procurement rebalances toward non-FCS environments, likely reflecting broader digital public infrastructure reforms and the scaling of GovTech in middle-income countries. CCT expands in both FCS and non-FCS contexts, aligning with the Human Capital agenda and shock-responsive social protection systems, particularly during COVID-19. PPP activity plateaus but remains structurally stronger in non-FCS, consistent with fiscal sustainability constraints and increasing scrutiny of contingent liabilities. Innovation in this period appears less about diffusion per se and more about contextual fit, risk calibration, and portfolio specialization under a more systematized fragility framework.

# Table F.2. Diffusion of Innovation Models in FCS vs. Non-FCS: Conditional Cash Transfers

| Decade | FCS Mentions | Non-FCS Mentions | Total |
| --- | --- | --- | --- |
| 1998-2007 | 0 | 0 | 0 |
| 2008-2017 | 3 | 14 | 17 |
| 2018-2025 | 8 | 21 | 29 |

# Table F.3. Diffusion of Innovation Models in FCS vs. Non-FCS: PPP

| Decade | FCS Mentions | Non-FCS Mentions | Total |
| --- | --- | --- | --- |
| 1998-2007 | 13 | 55 | 68 |
| 2008-2017 | 20 | 91 | 111 |
| 2018-2025 | 19 | 73 | 92 |

# Table F.4. Diffusion of Innovation Models in FCS vs. Non-FCS: E-Procurement

| Decade | FCS Mentions | Non-FCS Mentions | Total |
| --- | --- | --- | --- |
| 1998-2007 | 1 | 2 | 3 |
| 2008-2017 | 14 | 4 | 18 |
| 2018-2025 | 3 | 10 | 13 |

# Table F.5. Diffusion of Innovation Models in FCS vs. Non-FCS: CDD

| Decade | FCS Mentions | Non-FCS Mentions | Total |
| --- | --- | --- | --- |
| 1998-2007 | 2 | 25 | 27 |
| 2008-2017 | 20 | 58 | 78 |
| 2018-2025 | 17 | 28 | 45 |

Note: The time period 2028–2025 is a partial cohort, with many projects still under implementation.

Diffusing innovation into fragile states is harder, slower, and riskier. Yet, it has been made possible when three enabling conditions converge: (i) corporate reforms that lower the transaction costs of adopting innovation (e.g., new procurement and safeguards frameworks and the use of programmatic instruments); (ii) risk-sharing mechanisms that de-risk participation for governments and private actors (e.g., guarantees, blended finance, and third-party verification); and (iii) community-based or decentralized models that bypass weak central institutions (e.g., CDD programs and social funds).  Over time, these conditions have transformed fragile contexts from laggards into active participants in global innovation trends. The evidence reveals not a narrative of parity but of gradual convergence—fragile states progressively adopting, adapting, and scaling innovations once considered unattainable in their environments.

All findings and interpretations in this paper are solely those of the authors and do not necessarily represent the views of the World Bank, its Executive Directors, or the countries they represent. We are grateful for guidance and feedback provided by: Axel van Trotsenburg, Lisa Finneran, Ragini Dalal, Daniel Rogger, Richard Kohl, Sharada Srinivasan, Gary Milante, Miguel Purroy, Lindsey Jones, Imran Ali, Cordelia Chesnutt, and Farida Razaqi. Laura Lahoz Gonzalez provided excellent data and research assistance. Email addresses for correspondence: nagapitova@worldbank.org and eertekin@ifc.org.

Effectiveness is defined based on findings in the lessons and recurrence in the portfolio. At the project-level, effectiveness is linked to outcomes delivered with strong execution. At the portfolio-level, effectiveness is linked to interest in replication and evidence of larger scale (as indicated by more mentions).

The dataset is available at https://ieg.worldbankgroup.org/ieg-search-icrr (last accessed on February 8, 2026).

The dataset contains a limited number of earlier projects, primarily from the 1980s and one from the late 1970s, which were evaluated retrospectively between 1998 and 2008 after project closure.

Two of the original observations did not have any text in the lessons learned section of the report. These two observations were dropped from the dataset.

The dataset includes Investment Project Financing (IPF), Development Policy Financing (DPF), and Program-for-Results (PforR).

The models are listed in alphabetical order. The sequence does not reflect frequency of use, relative weight in the analysis, or performance ranking.

Examples of projects that are classified as innovative in our dataset include: Pakistan, Land Records Management and Information Systems Project (P090501); Estonia, Health Project (P008402); Lao PDR, Nam Theun 2 Power Project (P076445); Angola, Water Sector Institutional Development (P096360); Peru, Rural Roads Rehabilitation & Maintenance (P037047); Tunisia, Northwest Mountainous Areas Development Project (P005733).

Table D.1 in Appendix B shows the distribution of projects across all three categories of innovation: 87% low, 10% moderate, 3% high. We combine moderate and high into one category throughout this analysis.

The innovation types and corresponding lessons were surfaced with LLM support and verified by the authors.

Access to Finance for Recovery and Resilience Project (P175273).

The World Bank Regions were created by mapping each project’s country to the current World Bank regional classification. The mapping follows the latest World Bank List of Economies (2020) and subsequent regional split of Sub-Saharan Africa into Eastern and Southern Africa and Western and Central Africa. This coding is static and based on the most recent classification. It does not reflect historical changes in regional assignments, for example, the Sudan/South Sudan split or shifts in regional groupings used before 2020. As a result, regional counts represent today’s official classification applied retroactively across all project years. Projects are classified as “other” if they span more than one region.

The IDA and IBRD comparisons and lessons were informed by LLM outputs and supplemented by author review, analysis, and inputs.

An alternative explanation is that FCS projects focus on delivering basic services through well-tested models and that process innovations (e.g. implementation arrangements, financing) are more common than project design innovations in FCS contexts. Additional research is needed to explore this hypothesis.

PE-BASIC HLTH/NUTRITION, P008048; Andhra Pradesh and Telangana Municipal Development Project, P071250; Accelerating India's COVID-19 Social Protection Response Program (PMGKY), P173943

Figure 3.3 focuses on the nine GPs that have data across all cohorts and that have the highest overall prevalence of innovation. Digital and Social Sustainability and Inclusion are among the top nine innovative GPs overall, but they are excluded from Figure 3.3. because they are relatively new (<10 years old) GPs and therefore do not have data across all cohorts.

In this context, premium refers to the positive or negative effect that the presence of digital technology has on project performance outcomes

There are not any Digital Development projects that are classified as high or moderate innovation and that do not have a technology tag.

Findings and lessons on Trust Funds were surfaced with LLM support and reviewed and verified by the authors.

Emergency Education Rehabilitation & Development Project in Afghanistan, P077896; MOLDOVA REGIONAL DEVELOPMENT, P118405

Regional Coordination for Improved Water Resources Mgt. & Capacity (P130801).

Angola First Education Project (P000042).

National Minor Irrigation Development Project (P009544).

Republic of Congo Emergency Recovery and Community Support Project (P081924).

WOMEN IN DEVELOPMENT, P000822; Rural Poverty Alleviation – Ceara, P038884; ENVIRONMENTAL Management in Burkina Faso, P000290)

The Turn Around Allocation is a specific fund that supports countries emerging from a period of conflict, social/political crisis, or disengagement and where there is a window of opportunity for IDA to either re-engage or intensify support to pursue reforms that can accelerate a transition out of fragility and build resilience.

Lessons and analysis in this section were surfaced by LLM and reviewed and verified by the authors.

For Oslo classifications see OECD/Eurostat 2018.

For a description of Nesta’s innovation levels, see https://www.nesta.org.uk

The innovation content is not weighed as a share of lending envelope dedicated to innovation activities. Therefore, a project with “high” innovation content could dedicate only a portion of its funding to innovation, for example, through a subcomponent or an activity within a broader approach.